## Sheet1
Step | Method | Result (Board 1) | Result (Board 2) | Result (Board 3) | Result Rev 1 (Board 1) | Result Rev 1 (Board 2) | Result Rev 1 (Board 3) | Result Rev 2 (Board 1) | Result Rev 2 (Board 2) | Result Rev 2 (Board 3) | Result Rev 2 (Board 4) | Result Rev 2 (Board 5) | Result Rev 2 (Board 6)
Continuity Test | The continuity function on the team's personally owned multimeter will be used to test continuity across all nets to identify unentended shorts. The Component Net List spreadsheet will be used to reference all net component connections, along with the KiCad project files for visual reference. | Power, Antenna, Crystal, Doorbell, and Motion Sensor Circuits passed the test. -Luke | The Antenna, Power, Doorbell, and the Motion Sensor have passed the continuity test- Abdul | Power, Antenna, Crystal, JTAG, Doorbell, and Motion Sensor Circuits passed the test. -Luke | - C2, C28 dont have proper GND connection in KiCad (Island) - JTAG pins 4 and 2 questionable - Testing completed with noted errors and questionable connections | - C2, C28 dont have proper GND connection in KiCad (Island) - JTAG pins 4 and 2 questionable | - C2, C28 dont have proper GND connection in KiCad (Island) - JTAG pins 4 and 2 questionable | All points are checked out and working | All points are checked out and working | All points checked and continuity was found | All points checked and continuity was found | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Secure Stencil | Utilize scotch tape or adhesive alternative to secure the Stencil to the board. Ensure the stencil and board are aligned. | N/A Stencil Did not arrive in time | N/A Stencil Did not arrive in time | Stencil Secured using tape from packaging | Completed |  | Completed | Completed | Completed | Completed | Completed | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Spread Solder Paste | The solder paste spreader provided by OSH Park will be used to spread solder paste across pads. | N/A Stencil Did not arrive in time | N/A Stencil Did not arrive in time | Used Osh Stencil provided spreader. Paste spread well, not as well as expected. | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Completed with OSH Park provided spreader | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Place SMD Components | Tweezers will be used to place all SMD components. | Placed all SMD components | Placed all SMD components | Placed all SMD components | Completed - Luke M. and Ethan H. | Completed - Luke M. and Ethan H. | Completed - Abdul B. | Completed - Luke M. and Ethan H. | Completed - Luke M. and Ethan H. | Completed - Abdul B. and Ethan H. | Completed - Abdul B. and Luke M. | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Heat SMD Solder Joints | The team’s personally owned heat gun will be utilized to heat and connect SMD Solder joints. Kapton tape will be used to block soldered joints from the heatgun. | Heated Solder joints with heatgun | Heated Solder joints with heatgun | Heated solder joints with heatgun | Completed - Luke M. and Ethan H. | Completed - Luke M. and Ethan H. | Completed - Abdul B. | Completed - Luke M. and Ethan H. | Completed - Luke M. and Ethan H. | Completed - Abdul B. and Ethan H. | Completed - Abdul B. and Luke M. | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Solder Through-Hole Components | The team’s personally owned solder Iron and solder will be used to place through hole components. (EXCLUDING BATTERY HOLDERS) | Soldered Battery holders, power switch, U12 power test headers, SMA connector, U10 doorbell header, J3 Motion Sensor Header | Handed of board to Ethan before this step could be reached | Soldered power switch, U12 power test headers, SMA connector, U10 doorbell header, J3 Motion Sensor Header | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Completed - Luke M. and Ethan H. | Completed - Luke M. and Ethan H. | Completed - Abdul B. and Ethan H. | Completed - Abdul B. and Luke M. | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Doorbell Assembly | The external doorbell push button will be soldered to U10 utilizing the two pin wire leads. The order of connection for these leads does not matter. | Soldered wire connectors to the ends of the microphone where they need to be connected | N/A | Soldered wire connectors to the ends of the microphone where they need to be connected | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Waiting for further testing with computer engineers before assembly begins | Waiting for further testing with computer engineers before assembly begins | Problesm with software integration, could not integrate due to J-Tag connection | Problesm with software integration, Could not integrate due to J-Tag connection Could not integrate with DevKit | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Motion Sensor Assembly | The external motion sensor will be connected to the J3 4 pin male header utilizing the 4 pin wire leads. The Component Net List spreadsheet will be used to reference all net component connections, along with the KiCad project files for visual reference. The 4 pin wire leads must be connected to the 4 pin male header as follows: Pin1: 5V Pin2: TX Pin3:RX Pin4: GND | Soldered wire connectors to corresponding throughholes, 5V (wire 1), Rx (wire 2), Tx (wire 3),GND (wire 4), | N/A | Soldered wire connectors to corresponding throughholes, 5V (wire 1), Rx (wire 2), Tx (wire 3), GND (wire 4) | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Waiting for further testing with computer engineers before assembly begins | Waiting for further testing with computer engineers before assembly begins | Problesm with software integration, could not integrate due to J-Tag connection | Problesm with software integration, could not integrate due to J-Tag connection | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Speaker Assembly | The external speaker will be connected to j4 via 2 pin wire leads. The Component Net List spreadsheet will be used to reference all net component connections, along with the KiCad project files for visual reference. The wire leads must be connected as follows: Pin1: Negative terminal Pin2: Positive terminal | N/A | N/A | N/A | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Completed - Luke M. and Abdul B. | Waiting for further testing with computers before assembly begins | Waiting for further testing with computers before assembly begins | Problesm with software integration, could not integrate due to J-Tag connection | Problesm with software integration, could not integrate due to J-Tag connection | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose