## Sheet1
Step | Method | Result (Board 1) | Result (Board 3) | Result Rev. 1(Board 1) | Result Rev. 1 (Board 2) | Result Rev. 1 (Board 3) | Result Rev. 2 (Board 1) | Result Rev. 2 (Board 2) | Result Rev. 2 (Board 3) | Result (Board 4) | Result Rev. 2 (Board 5) | Result Rev. 2 (Board 6)
Short Circuit Analysis | The continuity function on the team's personally owned multimeter will be used to test continuity across all nets to identify unentended shorts. The Component Net List spreadsheet will be used to reference all net component connections, along with the KiCad project files for visual reference. | - V_source1 = 6V - V_source2 = 6V - 3.3V = no voltage - U17 Out = 3.97 (something wrong with pin) - 5V = 4V | Each point tested on the PCB had continuity | No shorts | No shorts | No shorts | No shorts pre-assembly | - No shorts pre-assembly - Post-assembly, their might be problems with 5V regulator | No shorts pre-assembly | No shorts pre-assembly | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Power | Pin 1 (V_Source1) of the J5 4 Pin header will be connected to a power supply set at 6V 0.5A via alligator clips. The negative terminal of the power supply will be connected to GND. The multimeter voltage and current sensing function will be used to measure and record the output voltages and currents throughout the power circuit. The individual battery voltages, voltage at netlits V_Source1, V_Source2, 6V, 5V, and 3.3V will be recorded. The 4 pin header J5 has individual pin connections for all netlists. | - V_source1 = 6V - V_source2 = 6V - 3.3V = no voltage - U17 Out = 3.97 (something wrong with pin) - 5V = 4V | - V_source1 = 6V - V_source2 = 6V - 3.3V = 0.49V - 5V = 2.5 - CR1 Diode = V drop of 3.5V - Pad 1 = 6V - Pad 2 = 2.5V - 2.5V entering both ICs - Diode dropping a lot - CR1 Diode initially installed backwards, after flipping diode, results were measured - Pad 2 diode voltage = 5.82V - J5 pin 4 measured at 4V - Pin 3 measured at 4V | - At 5V we are getting 3.6V - At 3.3V we are getting 3.4V - QPG6200L = 3.37V - Mic 3.87V - Audio = 3.87V - DAC = 3.87V - J-Tag = 3.87V - Doorbell = 3.48V - Motion sensor = 3.87V - 5V regulator input = 5.75V - 3.3V regulator input = 5.75V - 5V output regulator = 5.2V dropping slowly over time (due to capacitors?); a little over 4.7V - 3.3V = 3.88V | - At 5V source = 3.76 - 3.3V source = 3.56V - 3.56 = J-Tag - 3.56V QPG6200L - DAC = 3.56V - Doorbell = 3.56V (resolder) - 4V =Audio amp - 4V = motion sensor | - 5V = 4V - 3.3V = 3.69V - Mic = 3.66 - J-Tag = 3.65V - QPG = 3.6V - 3.62V = Doorbell - Motion sensor = 4V - DAC = 3.61V - Audio amp = 4V | - 3.3V read - J-Tag = 3.3V - PROG_ENn = 3.3V to 0.045V - Vref on JLINK is supposed to be 0V QPG6200 Internal pulls up nRESET pin (From datasheet pg 49) Dev kit is also getting 3.3V at nRESET pin, TDO, TDI Tested board programming - No J-Tag connection - J-Tag_nRESET and TMS has 3.3V reading (For first test, not on second) (NOT SHORTED) on board 1 - T-Tag nRESET is reading 3.3 (NOT TMS) (NO SHORT) Board 1 test 2: Error 1: Unable to read chip ID Error 2: pin override is not supported but required for the selected device Pins with ~3.3V: 3.3V pin, nRESET, TMS, TDO PROG_ENn switch cuts voltage from 3.3V to 0.045V | - 3.3V read - J-Tag = 3.3V - PROG_ENn = 3.3V to 0.045V - Vref on JLINK is supposed to be 0V QPG6200 Internal pulls up nRESET pin (From datasheet pg 49) Dev kit is also getting 3.3V at nRESET pin, TDO, TDI Tested board programming - No J-Tag connection - J-Tag_nRESET and TMS has 3.3V reading (For first test, not on second) (NOT SHORTED) on board 1 - T-Tag nRESET is reading 3.3 (NOT TMS) (NO SHORT) Board 1 test 2: Error 1: Unable to read chip ID Error 2: pin override is not supported but required for the selected device Pins with ~3.3V: 3.3V pin, nRESET, TMS, TDO PROG_ENn switch cuts voltage from 3.3V to 0.045V | - SW5 pulling 1.5A when powered on - SW5 is to remain off when using device | Assembled to be shown as example and prop, not to be shown for functionality | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
IC Power | Pin 1 (V_Source1) of the J5 4 Pin header will be connected to a power supply set at 6V 0.5A via alligator clips. The negative terminal of the power supply will be connected to GND. The multimeter voltage and current sensing function will be used to measure and record all voltages and currents across all IC components (U3, U4, U5, U16, U17, and U18). The Component Net List spreadsheet will be used to identify netlist and pad numbers for IC power inputs. The KiCad project files will be used for visual reference. | - U3 = 3.94V - U4 = 3.93V - U5 = Not using - U16 = 5.4V - U17 = 4.9V - U18 = not installed = 3.9V | - U3 = 3.9V going into QPG - U4 = 3.93V - U5 removed from design - U16 = 5.7V input - U16 = 3.9V output - U17 = 5.77V In - U17 = 3.92V Out - U18 = not installed - U18 = 3.92V In | - At 6V = 6V - At 5V = 4.99V - At 3.3V = 3.29V | Void (Needed new testing method) | Void (Needed new testing method) | Both power regulator are good | Error - unable to read power (problem wit 5V regulator) | Both power regulator are good | Assembled to be shown as example and prop, not to be shown for functionality | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
IC Overcurrent | The current limit on the power supply will be increased to 0.7A, and the previous steps for IC power will be repeated to identify any overcurrent possibilities. | Research alternative ways to measure current. | Research alternative ways to measure current. | 11mA across R1 | Void - board doesn’t support testing method | Void - board doesn’t support testing method | Did not conduct yet | Did not conduct due to IC and regulator problems | 7mA total = good | Assembled to be shown as example and prop, not to be shown for functionality | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
Battery Test | Install Batteries into battery holders, and repeat steps for power and IC power. Check batteries with a multimeter for 2.8+ Volts | - Redo footprints in KiCAD for batteries - Battery terminal footprints are incorrect, can’t be used | - 2.88V on battery 1 - 3.1V on battery 2 - Redo footprints in KiCAD for batteries - Battery terminal footprints are incorrect, can’t be used | Could not perform due to footprints and J-Tag pin | Could not perform due to footprints and J-Tag pin | Could not perform due to footprints and J-Tag pin | Battery power was good | Battery power was good | - 7.3V - Batteries are working with device | Assembled to be shown as example and prop, not to be shown for functionality | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose
SMA Impedance | The NanoVNA will be connected to the 50OHm SMA connector via the NanoVNA kit’s female to female connector. After connecting and acquiring a plot on the “SMITH R + jX” format in the 2.4Ghz to 2.5Ghz band, the data will be imported to the NanoVNA saver via usb cable. After the data is imported into the NanoVNA saver, the data will be saved and recorded for later use and reference. | The NanoVNA was successfully connected to the 50Ohm SMA connector. The data was then imported into the NanoVNA Saver and recorded the following data. Marker 1 Impedance: 27 + j37.8 Ohm S11 VSWR: 2.245 Return Loss: -8.321 dB -Luke M. | N/A | SMA Impedance: - 2.4 GHz: 15.5 + 22.5j - 2.5 GHz: 92.4 + 109j | SMA Impedance: - 2.4 GHz: 12.1 + 9.02 - 2.5 GHz: 44.4 + 85.1j | SMA Impedance: - 2.4 GHz: 273 - 316j - 2.5 GHz: 12.3 - 47.3j | Not conducted yet | Currently testing - no considerable changes were observed | - Inconclusive data, numebrs were not as expected due to connections on NANO VNA and SMA | Assembled to be shown as example and prop, not to be shown for functionality | Did not assemble due to PCB design not being funtional for intened purpose | Did not assemble due to PCB design not being funtional for intened purpose