## Timesheet Dashboard
Timesheet Dashboard for: |  |  | QORVO_RADIO2
Download in Excel
Fill in Team Name and Team Members Names on this page only
Last, First (aplha order)
Team Member Name | Timesheet 1 | Timesheet 2 | Timesheet 3 | Timesheet 4 | Timesheet 5 | Total
Bah, Abdul | 22 | 31.75 | 36.5 | 22.5 | 24.75 | 137.5
Hartman, Ethan | 16 | 27 | 40.5 | 18.75 | 0 | 102.25
Hernandez, Alberto | 32.5 | 46.75 | 48.5 | 39.5 | 38.25 | 205.5
Le, Kenneth | 30.25 | 37.25 | 39.75 | 31.6667 | 31.25 | 170.1667
Matthews, Luke | 22.25 | 39 | 60.25 | 27.5 | 31.75 | 180.75
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
WBS Element | Timesheet 1 | Timesheet 2 | Timesheet 3 | Timesheet 4 | Timesheet 5 | Total
ANALYSIS | 0 | 2 | 0 | 0 | 0 | 2
ASSEMBLY | 0 | 13.5 | 28.25 | 0 | 19 | 60.75
DESIGN | 9.25 | 11.75 | 26.75 | 10.25 | 0 | 58
DOCUMENT - ADMIN | 4.75 | 20.5 | 23 | 57.75 | 30 | 136
DOCUMENT - TECH | 3.5 | 13.75 | 9 | 1.25 | 0 | 27.5
FABRICATION | 0 | 23.75 | 0 | 0 | 0 | 23.75
MENTOR | 0 | 7.5 | 5.75 | 4.5 | 3.25 | 21
OUTREACH | 0 | 0 | 0 | 0 | 0 | 0
PLAN | 18.25 | 7 | 14.75 | 17.8333 | 12.75 | 70.5833
PROCUREMENT | 5 | 1.75 | 3.5 | 2.25 | 0.5 | 13
PROGRAMMING/ SOFTWARE | 47 | 41.75 | 54 | 22.5 | 30 | 195.25
RESEARCH | 27.25 | 29.25 | 12 | 13 | 3.5 | 85
SOW | 0 | 0 | 0 | 0 | 0 | 0
SUPPORTER | 8 | 8 | 39.5 | 5.0833 | 24 | 84.5833
TEST | 0 | 0.25 | 8.5 | 0 | 3 | 11.75

## Timesheet 1
Team Member Name | Total Timesheet Hours | Timesheet 1 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Bah, Abdul | 22 | QORVO_RADIO2 | ANALYSIS | 0
Hartman, Ethan | 16 |  | ASSEMBLY | 0
Hernandez, Alberto | 32.5 |  | DESIGN | 9.25
Le, Kenneth | 30.25 |  | DOCUMENT - ADMIN | 4.75
Matthews, Luke | 22.25 |  | DOCUMENT - TECH | 3.5
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 0
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 18.25
| 0 |  | PROCUREMENT | 5
|  |  | PROGRAMMING/ SOFTWARE | 47
|  |  | RESEARCH | 27.25
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 8
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2026-01-12 | Matthews, Luke | Meeting with Tanner from ISL |  | 9:30 | 10:00 | 0.5 | PROCUREMENT
2026-01-13 | Matthews, Luke | PCB Order check in |  | 11:00 | 11:15 | 0.25 | PROCUREMENT
2026-01-14 | Matthews, Luke | PCB Order Check in |  | 12:15 | 12:30 | 0.25 | PROCUREMENT
2026-01-14 | Matthews, Luke | PCB Order update email to mentor |  | 15:15 | 15:30 | 0.25 | PROCUREMENT
2026-01-14 | Matthews, Luke | Meeting with Tanner and Amanda Keys |  | 15:45 | 16:15 | 0.5 | PROCUREMENT
2026-01-15 | Matthews, Luke | Meeting with Abdul |  | 14:30 | 15:30 | 1 | PLAN
2026-01-15 | Matthews, Luke | Alternate PCB manufacturing research |  | 13:30 | 14:30 | 1 | RESEARCH
2026-01-15 | Matthews, Luke | OSH Park Quote and PR creation |  | 17:15 | 17:30 | 0.25 | PROCUREMENT
2026-01-18 | Matthews, Luke | Stretch goals research |  | 15:00 | 17:00 | 2 | RESEARCH
2026-01-19 | Matthews, Luke | LO strecth goal research |  | 11:30 | 14:00 | 2.5 | RESEARCH
2026-01-20 | Matthews, Luke | LO strecth goal research |  | 10:00 | 11:00 | 1 | RESEARCH
2026-01-20 | Matthews, Luke | PCB Spec research |  | 13:45 | 14:15 | 0.5 | RESEARCH
2026-01-20 | Matthews, Luke | Meeting with Abdul |  | 14:15 | 14:45 | 0.5 | PLAN
2026-01-21 | Matthews, Luke | FPGA Research |  | 12:30 | 14:15 | 1.75 | RESEARCH
2026-01-22 | Matthews, Luke | Stencil manufacturing research |  | 13:00 | 14:00 | 1 | RESEARCH
2026-01-16 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-14 | Matthews, Luke | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-21 | Matthews, Luke | Team Meeting and meeting prep |  | 14:15 | 15:00 | 0.75 | PLAN
2026-01-21 | Matthews, Luke | PR creation |  | 15:00 | 15:15 | 0.25 | PROCUREMENT
2026-01-22 | Matthews, Luke | Meet with Abdul |  | 14:00 | 14:45 | 0.75 | PLAN
2026-01-22 | Matthews, Luke | Sponser slide prep |  | 21:00 | 21:30 | 0.5 | DOCUMENT - ADMIN
2026-01-14 | Hernandez, Alberto | Doorbell App Creation |  | 18:45 | 22:30 | 3.75 | PROGRAMMING/ SOFTWARE
2026-01-15 | Hernandez, Alberto | Gateway Research |  | 22:30 | 23:45 | 1.25 | RESEARCH
2026-01-19 | Hernandez, Alberto | UART COM |  | 15:00 | 20:00 | 5 | PROGRAMMING/ SOFTWARE
2026-01-14 | Hernandez, Alberto | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-21 | Hernandez, Alberto | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-22 | Hernandez, Alberto | BLE COM Firmware |  | 18:00 | 22:00 | 4 | PROGRAMMING/ SOFTWARE
2026-01-16 | Hernandez, Alberto | Implementation Plan |  | 9:00 | 12:15 | 3.25 | DESIGN
2026-01-16 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-22 | Hernandez, Alberto | Slide Creation |  | 22:15 | 23:15 | 1 | DOCUMENT - ADMIN
2026-01-23 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-23 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-27 | Matthews, Luke | Assembly and Test doc creation |  | 13:00 | 15:00 | 2 | DOCUMENT - ADMIN
2026-01-27 | Matthews, Luke | Antenna testing research |  | 15:00 | 15:15 | 0.25 | RESEARCH
2026-01-27 | Matthews, Luke | Email corrospondence with ISL |  | 15:15 | 15:30 | 0.25 | PROCUREMENT
2026-01-27 | Hernandez, Alberto | BLE Configuration |  | 9:00 | 11:00 | 2 | PROGRAMMING/ SOFTWARE
2026-01-28 | Hernandez, Alberto | BLE COM w App |  | 17:00 | 19:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-01-29 | Matthews, Luke | Email corrospondence with ISL |  | 15:15 | 15:30 | 0.25 | PROCUREMENT
2026-01-29 | Matthews, Luke | Email corrospondence with ISL |  | 15:45 | 16:00 | 0.25 | PROCUREMENT
2026-01-29 | Matthews, Luke | Team Meeting |  | 18:45 | 19:30 | 0.75 | PLAN
2026-01-29 | Matthews, Luke | Meet with Abdul |  | 19:30 | 19:45 | 0.25 | PLAN
2026-01-29 | Matthews, Luke | Sponsor slide prep |  | 20:00 | 20:30 | 0.5 | DOCUMENT - ADMIN
2026-01-29 | Hernandez, Alberto | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-01-29 | Hernandez, Alberto | BLE Central Device |  | 21:00 | 23:45 | 2.75 | PROGRAMMING/ SOFTWARE
2026-01-30 | Hernandez, Alberto | BLE Central device troubleshooting |  | 0:00 | 3:00 | 3 | PROGRAMMING/ SOFTWARE
2026-01-30 | Hernandez, Alberto | Slide Creation |  | 3:00 | 3:45 | 0.75 | DOCUMENT - ADMIN
2026-01-30 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:45 | 0.75 | SUPPORTER
2026-01-12 | Le, Kenneth | Gateway Setup |  | 17:30 | 23:00 | 5.5 | PROGRAMMING/ SOFTWARE
2026-01-13 | Le, Kenneth | Gateway Setup |  | 19:00 | 23:30 | 4.5 | PROGRAMMING/ SOFTWARE
2026-01-14 | Le, Kenneth | Gateway Setup with Mentor Aid |  | 17:00 | 20:30 | 3.5 | PROGRAMMING/ SOFTWARE
2026-01-14 | Le, Kenneth | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-15 | Le, Kenneth | Router Setup with Mentor |  | 15:30 | 19:30 | 4 | PROGRAMMING/ SOFTWARE
2026-01-15 | Le, Kenneth | Slide Creation |  | 21:30 | 22:30 | 1 | DOCUMENT - TECH
2026-01-16 | Le, Kenneth | Router Setup with Mentor |  | 14:30 | 17:30 | 3 | PROGRAMMING/ SOFTWARE
2026-01-16 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-21 | Le, Kenneth | Team Meeting and meeting prep |  | 14:15 | 15:00 | 0.75 | PLAN
2026-01-22 | Le, Kenneth | Firmware Development on Gateway |  | 17:30 | 19:00 | 1.5 | PROGRAMMING/ SOFTWARE
2026-01-23 | Le, Kenneth | Firmware Development on Gateway |  | 12:00 | 14:00 | 2 | PROGRAMMING/ SOFTWARE
2026-01-30 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:45 | 0.75 | SUPPORTER
2026-01-23 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-29 | Le, Kenneth | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-01-29 | Le, Kenneth | Device Connections to Gateway Research |  | 20:00 | 21:30 | 1.5 | RESEARCH
2026-01-30 | Le, Kenneth | Gateway to Laptop Connection Research |  | 10:00 | 11:00 | 1 | RESEARCH
2026-01-30 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:45 | 0.75 | SUPPORTER
2026-01-29 | Bah, Abdul | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-01-29 | Bah, Abdul | Electrical meeting |  | 19:30 | 19:45 | 0.25 | PLAN
2026-01-29 | Bah, Abdul | Slides |  | 23:00 | 23:30 | 0.5 | PLAN
2026-01-28 | Bah, Abdul | Component Research |  | 14:00 | 16:00 | 2 | RESEARCH
2026-01-27 | Bah, Abdul | PLC Assembly Doc Review |  | 20:00 | 21:00 | 1 | DOCUMENT - TECH
2026-01-26 | Bah, Abdul | Component Research |  | 17:00 | 19:00 | 2 | RESEARCH
2026-01-26 | Bah, Abdul | Component Research |  | 21:00 | 22:30 | 1.5 | RESEARCH
2026-01-24 | Bah, Abdul | Component Research |  | 16:30 | 17:00 | 0.5 | RESEARCH
2026-01-23 | Bah, Abdul | Component Research |  | 10:00 | 10:30 | 0.5 | RESEARCH
2026-01-23 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-22 | Bah, Abdul | Electrical meeting |  | 14:00 | 15:00 | 1 | PLAN
2026-01-21 | Bah, Abdul | PCB Research and assembly planning |  | 12:00 | 12:30 | 0.5 | PLAN
2026-01-20 | Bah, Abdul | Electrical meeting |  | 14:00 | 14:45 | 0.75 | PLAN
2026-01-21 | Bah, Abdul | Stretch Goal Component Research |  | 13:00 | 14:30 | 1.5 | RESEARCH
2026-01-15 | Bah, Abdul | Electrical meeting |  | 14:30 | 15:30 | 1 | PLAN
2026-01-21 | Bah, Abdul | Team Meeting |  | 14:15 | 15:00 | 0.75 | PLAN
2026-01-16 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-14 | Bah, Abdul | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-23 | Bah, Abdul | LO, IC, I/O Stretch Goal Research |  | 16:00 | 17:30 | 1.5 | RESEARCH
2026-01-24 | Bah, Abdul | LO, IC, I/O Stretch Goal Research |  | 12:00 | 14:00 | 2 | RESEARCH
2026-01-24 | Bah, Abdul | PCB Assembly Research |  | 19:00 | 20:00 | 1 | RESEARCH
2026-01-30 | Bah, Abdul | PCB Assembly Research |  | 9:00 | 10:00 | 1 | RESEARCH
0
0
0
0
0
0
2026-01-14 | Hartman, Ethan | Team Meeting |  | 14:30 | 15:00 | 0.5 | PLAN
2026-01-16 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-21 | Hartman, Ethan | Team Meeting |  | 14:15 | 15:00 | 0.75 | PLAN
2026-01-23 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-01-29 | Hartman, Ethan | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-01-30 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:45 | 0.75 | SUPPORTER
2026-01-15 | Hartman, Ethan | Kickoff Assignment Work |  | 19:30 | 21:00 | 1.5 | DOCUMENT - TECH
2026-01-21 | Hartman, Ethan | PR Update and Submittal |  | 15:30 | 16:30 | 1 | PROCUREMENT
2026-01-18 | Hartman, Ethan | Weekly Preparation |  | 21:00 | 22:30 | 1.5 | PLAN
2026-01-25 | Hartman, Ethan | Weekly Preparation |  | 21:00 | 22:30 | 1.5 | PLAN
2026-01-27 | Hartman, Ethan | PR Pickup and Review |  | 11:30 | 12:30 | 1 | PROCUREMENT
2026-01-24 | Hartman, Ethan | Enclosure Design Updates |  | 14:00 | 18:00 | 4 | DESIGN
2026-01-25 | Hartman, Ethan | Drawing Updates |  | 14:00 | 16:00 | 2 | DESIGN
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 2
Team Member Name | Total Timesheet Hours | Timesheet 2 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Bah, Abdul | 31.75 | QORVO_RADIO2 | ANALYSIS | 2
Hartman, Ethan | 27 |  | ASSEMBLY | 13.5
Hernandez, Alberto | 46.75 |  | DESIGN | 11.75
Le, Kenneth | 37.25 |  | DOCUMENT - ADMIN | 20.5
Matthews, Luke | 39 |  | DOCUMENT - TECH | 13.75
| 0 |  | FABRICATION | 23.75
| 0 |  | MENTOR | 7.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 7
| 0 |  | PROCUREMENT | 1.75
|  |  | PROGRAMMING/ SOFTWARE | 41.75
|  |  | RESEARCH | 29.25
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 8
|  | remove example team and timesheet entry | TEST | 0.25
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2026-02-03 | Matthews, Luke | Meet with Abdul |  | 14:30 | 15:30 | 1 | PLAN
2026-02-04 | Matthews, Luke | Mentor Slide prep |  | 0:30 | 0:45 | 0.25 | DOCUMENT - ADMIN
2026-02-04 | Matthews, Luke | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-02-04 | Matthews, Luke | Picked up PR 9 and checked in on PR 10 status |  | 11:00 | 11:15 | 0.25 | PROCUREMENT
2026-02-04 | Matthews, Luke | Requested Quotes for various US based PCB manufactures |  | 12:30 | 13:00 | 0.5 | RESEARCH
2026-02-05 | Matthews, Luke | PCB Assembly | 4.1 | 17:30 | 23:45 | 6.25 | FABRICATION
2026-02-03 | Bah, Abdul | Electrical Meeting with Luke |  | 14:30 | 15:30 | 1 | PLAN
2026-02-04 | Bah, Abdul | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-02-05 | Bah, Abdul | PCB Assembly | 4.1 | 17:30 | 23:45 | 6.25 | FABRICATION
2026-02-05 | Matthews, Luke | Sponsor Slide Prep |  | 23:44 | 23:59 | 0.25 | DOCUMENT - ADMIN
2026-02-06 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-02-06 | Matthews, Luke | Minutes of the Meeting |  | 9:30 | 9:45 | 0.25 | DOCUMENT - ADMIN
2026-02-06 | Matthews, Luke | Email to Supporter |  | 9:45 | 10:00 | 0.25 | SUPPORTER
2026-02-06 | Matthews, Luke | PR 13 Creation |  | 10:00 | 10:15 | 0.25 | DOCUMENT - ADMIN
2026-02-06 | Matthews, Luke | PCB Assembly | 4.1 | 19:45 | 23:00 | 3.25 | FABRICATION
2026-02-06 | Bah, Abdul | PCB Assembly | 4.1 | 21:00 | 23:00 | 2 | FABRICATION
2026-02-06 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-02-09 | Matthews, Luke | Audio Amp Circuit Redesign Research |  | 14:15 | 17:00 | 2.75 | RESEARCH
2026-02-09 | Bah, Abdul | Inventory |  | 21:00 | 22:00 | 1 | DOCUMENT - ADMIN
2026-02-09 | Bah, Abdul | PCB Testing | 4.1 | 22:00 | 22:15 | 0.25 | TEST
2026-02-10 | Matthews, Luke | Footprint Downloads |  | 10:15 | 11:15 | 1 | DESIGN
2026-02-10 | Matthews, Luke | Mentor Slide prep |  | 15:30 | 15:45 | 0.25 | DOCUMENT - ADMIN
2026-02-11 | Matthews, Luke | Minutes of the meeting creation and prep |  | 7:45 | 8:00 | 0.25 | DOCUMENT - ADMIN
2026-02-11 | Matthews, Luke | Mentor Meeting |  | 8:00 | 8:30 | 0.5 | MENTOR
2026-02-11 | Matthews, Luke | Footprint downloads and quality check |  | 12:00 | 13:15 | 1.25 | DESIGN
2026-02-11 | Matthews, Luke | Audio Amp KiCad Schematic development |  | 14:30 | 17:00 | 2.5 | DESIGN
2026-02-12 | Matthews, Luke | KiCad Audio amp schematic and PCB editor development |  | 14:00 | 15:30 | 1.5 | DESIGN
2026-02-12 | Matthews, Luke | KiCad Audio amp PCB editor development |  | 17:30 | 19:00 | 1.5 | DESIGN
2026-02-12 | Matthews, Luke | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-02-12 | Matthews, Luke | Sponsor slide prep |  | 21:00 | 21:30 | 0.5 | DOCUMENT - ADMIN
2026-02-13 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-13 | Matthews, Luke | KiCad Audio amp PCB editor development |  | 12:00 | 13:00 | 1 | DESIGN
2026-02-15 | Matthews, Luke | PDR Slide prep |  | 22:00 | 22:30 | 0.5 | DOCUMENT - ADMIN
2026-02-16 | Matthews, Luke | PDR Slide prep |  | 14:15 | 16:00 | 1.75 | DOCUMENT - ADMIN
2026-02-16 | Matthews, Luke | Microphone assembly |  | 16:00 | 16:45 | 0.75 | ASSEMBLY
2026-02-17 | Matthews, Luke | PR #13 Pick up |  | 10:00 | 10:15 | 0.25 | PROCUREMENT
2026-02-17 | Matthews, Luke | PSR Slide prep |  | 10:15 | 10:30 | 0.25 | DOCUMENT - ADMIN
2026-02-11 | Bah, Abdul | Mentor Meeting |  | 8:00 | 8:30 | 0.5 | MENTOR
2026-02-12 | Bah, Abdul | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-02-12 | Bah, Abdul | Sponsor meeting slides |  | 20:00 | 20:30 | 0.5 | PLAN
2026-02-13 | Bah, Abdul | PCB | 4.1 | 0:00 | 0:30 | 0.5 | DOCUMENT - ADMIN
2026-02-13 | Bah, Abdul | PCB testing and assembly | 4.1 | 16:00 | 18:00 | 2 | ASSEMBLY
2026-02-13 | Bah, Abdul | Electrical Meeting with Luke |  | 21:00 | 21:30 | 0.5 | PLAN
2026-02-14 | Bah, Abdul | PCB user interface assembly | 4.1 | 16:15 | 17:45 | 1.5 | ASSEMBLY
2026-02-16 | Bah, Abdul | PSR Slide prep |  | 17:00 | 18:00 | 1 | DOCUMENT - ADMIN
2026-02-16 | Bah, Abdul | PSR Slide prep |  | 22:00 | 23:00 | 1 | DOCUMENT - ADMIN
2026-02-17 | Bah, Abdul | PSR Slide prep |  | 0:00 | 1:45 | 1.75 | DOCUMENT - ADMIN
2026-02-17 | Bah, Abdul | PCB Assembly | 4.1 | 17:45 | 20:45 | 3 | ASSEMBLY
2026-02-17 | Matthews, Luke | PCB Assembly and KICad redesign | 4.1 | 17:30 | 20:45 | 3.25 | ASSEMBLY
2026-02-18 | Matthews, Luke | Mentor Meeting |  | 8:00 | 8:45 | 0.75 | MENTOR
2026-02-18 | Matthews, Luke | PR 16 order with ISL |  | 15:30 | 15:45 | 0.25 | PROCUREMENT
2026-02-18 | Bah, Abdul | Mentor Meeting |  | 8:00 | 8:45 | 0.75 | MENTOR
2026-02-18 | Bah, Abdul | PSR slides |  | 15:00 | 15:30 | 0.5 | DOCUMENT - ADMIN
2026-02-19 | Bah, Abdul | PSR slides |  | 1:30 | 2:00 | 0.5 | DOCUMENT - ADMIN
2026-02-19 | Matthews, Luke | PSR Slides |  | 14:00 | 15:15 | 1.25 | DOCUMENT - ADMIN
2026-02-03 | Hernandez, Alberto | Mentor Slide prep |  | 20:30 | 21:30 | 1 | DOCUMENT - ADMIN
2026-02-04 | Hernandez, Alberto | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-02-04 | Hernandez, Alberto | BLE Host and Controller development | 4.2c | 10:00 | 11:30 | 1.5 | PROGRAMMING/ SOFTWARE
2026-02-04 | Hernandez, Alberto | BLE Host and Controller development | 4.2c | 16:00 | 18:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-05 | Hernandez, Alberto | Creating Zigbee Application | 4.2 | 9:00 | 11:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-02-05 | Hernandez, Alberto | Started creating Thread application | 4.2d | 19:00 | 22:00 | 3 | PROGRAMMING/ SOFTWARE
2026-02-06 | Hernandez, Alberto | Sponsor slide prep |  | 2:00 | 2:30 | 0.5 | DOCUMENT - ADMIN
2026-02-06 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-02-09 | Hernandez, Alberto | Researched UI platform |  | 8:30 | 11:30 | 3 | RESEARCH
2026-02-10 | Hernandez, Alberto | Choosing UI platform |  | 20:30 | 22:00 | 1.5 | RESEARCH
2026-02-10 | Hernandez, Alberto | Mentor meeting slide prep |  | 22:00 | 22:30 | 0.5 | DOCUMENT - ADMIN
2026-02-11 | Hernandez, Alberto | Mentor meeting |  | 8:00 | 8:30 | 0.5 | MENTOR
2026-02-12 | Hernandez, Alberto | Gateway alternative research |  | 9:00 | 13:00 | 4 | RESEARCH
2026-02-12 | Hernandez, Alberto | User interface integration |  | 21:30 | 23:30 | 2 | RESEARCH
2026-02-12 | Hernandez, Alberto | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-02-13 | Hernandez, Alberto | Sponsor meeting slides |  | 0:00 | 0:30 | 0.5 | DOCUMENT - ADMIN
2026-02-16 | Hernandez, Alberto | Mirophone firmware | 4.2e | 8:30 | 11:30 | 3 | PROGRAMMING/ SOFTWARE
2026-02-16 | Hernandez, Alberto | Speaker Firmware | 4.2f | 15:00 | 17:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-16 | Hernandez, Alberto | Thread Firmware Integration | 4.2d | 19:00 | 20:00 | 1 | PROGRAMMING/ SOFTWARE
2026-02-17 | Hernandez, Alberto | Raspberry Pi Integration research | 4.3 | 8:00 | 10:00 | 2 | RESEARCH
2026-02-17 | Hernandez, Alberto | PSR Slides |  | 10:00 | 11:30 | 1.5 | DOCUMENT - ADMIN
2026-02-19 | Bah, Abdul | PSR Slides |  | 20:30 | 21:00 | 0.5 | DOCUMENT - ADMIN
2026-02-19 | Bah, Abdul | PCB J-Link Assembly | 4.1 | 17:30 | 18:30 | 1 | ASSEMBLY
2026-02-19 | Bah, Abdul | Peer Evaluation |  | 21:45 | 22:15 | 0.5 | DOCUMENT - ADMIN
2026-02-18 | Hernandez, Alberto | Mentor Meeting |  | 8:00 | 8:45 | 0.75 | MENTOR
2026-02-18 | Hernandez, Alberto | Raspberry Pi Integration research |  | 10:00 | 13:00 | 3 | RESEARCH
2026-02-19 | Hernandez, Alberto | Technical Documentation for Iot Gateway Stack | 4.3 | 14:00 | 15:45 | 1.75 | DOCUMENT - TECH
2026-02-19 | Hernandez, Alberto | Technical Documentation for Iot Gateway Stack | 4.3 | 16:30 | 18:45 | 2.25 | DOCUMENT - TECH
2026-02-19 | Hernandez, Alberto | Demo Preparation |  | 19:30 | 21:15 | 1.75 | PROGRAMMING/ SOFTWARE
2026-02-19 | Hernandez, Alberto | Peer Evaluation |  | 21:15 | 21:45 | 0.5 | DOCUMENT - ADMIN
2026-02-19 | Hernandez, Alberto | Demo Preparation |  | 22:00 | 23:30 | 1.5 | PROGRAMMING/ SOFTWARE
2026-02-20 | Hernandez, Alberto | Github Oraganizing |  | 0:00 | 0:45 | 0.75 | DOCUMENT - ADMIN
2026-02-20 | Hernandez, Alberto | PSR |  | 9:00 | 10:00 | 1 | SUPPORTER
2026-02-19 | Bah, Abdul | PCB Doc review |  | 20:00 | 20:30 | 0.5 | DOCUMENT - ADMIN
2026-02-20 | Bah, Abdul | PSR Slide prep |  | 0:00 | 0:15 | 0.25 | DOCUMENT - ADMIN
2026-02-19 | Matthews, Luke | J-Link assmebly | 4.1 | 17:30 | 18:30 | 1 | ASSEMBLY
2026-02-20 | Matthews, Luke | PSR |  | 9:00 | 10:00 | 1 | SUPPORTER
2026-02-20 | Matthews, Luke | Peer Evaluation |  | 12:30 | 13:00 | 0.5 | DOCUMENT - ADMIN
2026-02-02 | Le, Kenneth | Gateway Development | 4.3 | 14:00 | 16:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-03 | Le, Kenneth | Gateway Development | 4.3 | 14:00 | 16:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-04 | Le, Kenneth | Programming Kit Development | 4.3 | 17:30 | 19:30 | 2 | PROGRAMMING/ SOFTWARE
2026-02-05 | Le, Kenneth | Programming Kit Development | 4.3 | 14:00 | 16:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-06 | Le, Kenneth | Programming Kit Development | 4.3 | 17:00 | 19:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-04 | Le, Kenneth | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-02-06 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-02-09 | Le, Kenneth | Programming Kit Development | 4.3 | 13:00 | 14:30 | 1.5 | PROGRAMMING/ SOFTWARE
2026-02-10 | Le, Kenneth | nrF5280 Module Research | 4.3 | 14:00 | 16:00 | 2 | RESEARCH
2026-02-11 | Le, Kenneth | nrF5280 Module Research | 4.3 | 17:30 | 19:30 | 2 | RESEARCH
2026-02-12 | Le, Kenneth | Gateway Alternative Research | 4.3 | 14:00 | 16:00 | 2 | RESEARCH
2026-02-13 | Le, Kenneth | Gateway Alternative Research | 4.3 | 17:00 | 19:00 | 2 | RESEARCH
2026-02-13 | Le, Kenneth | Sponsor meeting slides |  | 0:00 | 0:30 | 0.5 | DOCUMENT - ADMIN
2026-02-11 | Le, Kenneth | Mentor meeting |  | 8:00 | 8:30 | 0.5 | MENTOR
2026-02-13 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-16 | Le, Kenneth | Raspberry Pi Gateway Research | 4.3a | 10:00 | 12:00 | 2 | RESEARCH
2026-02-17 | Le, Kenneth | PSR Slides |  | 20:00 | 23:00 | 3 | PROGRAMMING/ SOFTWARE
2026-02-18 | Le, Kenneth | Node-Red Download & Programming | 4.3b | 19:00 | 23:00 | 4 | PROGRAMMING/ SOFTWARE
2026-02-19 | Le, Kenneth | Node-Red Demo Creation | 4.3b | 18:00 | 20:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-20 | Le, Kenneth | Node-Red Demo Creation | 4.3b | 20:00 | 23:00 | 3 | PROGRAMMING/ SOFTWARE
2026-02-20 | Le, Kenneth | PSR Presentation |  | 9:00 | 10:00 | 1 | SUPPORTER
2026-02-18 | Le, Kenneth | Mentor Meeting |  | 8:00 | 8:45 | 0.75 | MENTOR
2026-02-20 | Bah, Abdul | PSR |  | 9:00 | 10:00 | 1 | SUPPORTER
2026-02-20 | Bah, Abdul | Inventory |  | 12:30 | 13:00 | 0.5 | DOCUMENT - ADMIN
2026-02-20 | Bah, Abdul | NanoVNA Research |  | 13:45 | 14:15 | 0.5 | RESEARCH
2026-02-03 | Hartman, Ethan | Mentor meeting slide prep |  | 22:00 | 22:15 | 0.25 | DOCUMENT - TECH
2026-02-04 | Hartman, Ethan | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-02-05 | Hartman, Ethan | PCB Measurement Verification |  | 19:00 | 20:00 | 1 | ANALYSIS
2026-02-05 | Hartman, Ethan | Display Assembly |  | 20:00 | 21:00 | 1 | ASSEMBLY
2026-02-05 | Hartman, Ethan | Sponsor Meeting slide prep |  | 23:00 | 23:15 | 0.25 | DOCUMENT - TECH
2026-02-06 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-02-07 | Hartman, Ethan | PCB Redisign from PCB measurements |  | 14:00 | 17:00 | 3 | DESIGN
2026-02-07 | Hartman, Ethan | 3D Printing Prep | 4.5 | 18:00 | 18:30 | 0.5 | FABRICATION
2026-02-08 | Hartman, Ethan | 3D Printing Postprocessing | 4.6 | 14:00 | 15:00 | 1 | FABRICATION
2026-02-10 | Hartman, Ethan | PCB Measurement Verification |  | 14:00 | 15:00 | 1 | ANALYSIS
2026-02-10 | Hartman, Ethan | Mentor meeting slide prep |  | 23:00 | 23:15 | 0.25 | DOCUMENT - TECH
2026-02-11 | Hartman, Ethan | Mentor Meeting |  | 8:00 | 8:30 | 0.5 | MENTOR
2026-02-11 | Hartman, Ethan | 3D Printing Prep | 4.5 | 15:00 | 15:30 | 0.5 | FABRICATION
2026-02-11 | Hartman, Ethan | 3D Printing Postprocessing | 4.6 | 21:00 | 22:00 | 1 | FABRICATION
2026-02-12 | Hartman, Ethan | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-02-12 | Hartman, Ethan | Sponsor Meering Slide Prep |  | 22:00 | 22:30 | 0.5 | DOCUMENT - TECH
2026-02-13 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-13 | Hartman, Ethan | 3D Printing Prep | 4.5 | 11:30 | 12:00 | 0.5 | FABRICATION
2026-02-13 | Hartman, Ethan | 3D Printing Postprocessing | 4.6 | 17:00 | 18:00 | 1 | FABRICATION
2026-02-14 | Hartman, Ethan | PSR Slide Prep |  | 13:00 | 16:00 | 3 | DOCUMENT - TECH
2026-02-15 | Hartman, Ethan | 3D Printing Prep | 4.5 | 13:00 | 13:30 | 0.5 | FABRICATION
2026-02-15 | Hartman, Ethan | 3D Printing Postprocessing | 4.6 | 19:00 | 20:00 | 1 | FABRICATION
2026-02-16 | Hartman, Ethan | PSR Slide Prep |  | 12:00 | 14:00 | 2 | DOCUMENT - TECH
2026-02-17 | Hartman, Ethan | PSR Slide Prep |  | 16:00 | 17:00 | 1 | DOCUMENT - TECH
2026-02-18 | Hartman, Ethan | Mentor Meeting |  | 8:00 | 8:45 | 0.75 | MENTOR
2026-02-18 | Hartman, Ethan | PO forms |  | 10:00 | 11:00 | 1 | PROCUREMENT
2026-02-19 | Hartman, Ethan | PSR Slide Prep |  | 15:00 | 17:00 | 2 | DOCUMENT - TECH
2026-02-19 | Hartman, Ethan | Additional PSR Material |  | 17:00 | 17:30 | 0.5 | DOCUMENT - TECH
2026-02-20 | Hartman, Ethan | PSR |  | 9:00 | 10:00 | 1
2026-03-20 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 3
Team Member Name | Total Timesheet Hours | Timesheet 3 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Bah, Abdul | 36.5 | QORVO_RADIO2 | ANALYSIS | 0
Hartman, Ethan | 40.5 |  | ASSEMBLY | 28.25
Hernandez, Alberto | 48.5 |  | DESIGN | 26.75
Le, Kenneth | 39.75 |  | DOCUMENT - ADMIN | 23
Matthews, Luke | 60.25 |  | DOCUMENT - TECH | 9
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 5.75
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 14.75
| 0 |  | PROCUREMENT | 3.5
|  |  | PROGRAMMING/ SOFTWARE | 54
|  |  | RESEARCH | 12
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 39.5
|  | remove example team and timesheet entry | TEST | 8.5
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2026-02-23 | Matthews, Luke | J-Link assembly | 4.1d | 20:45 | 22:45 | 2 | ASSEMBLY
2026-02-24 | Matthews, Luke | Project Plan update |  | 10:00 | 10:30 | 0.5 | DOCUMENT - ADMIN
2026-02-24 | Matthews, Luke | Mentor Meeting |  | 12:45 | 13:45 | 1 | MENTOR
2026-02-24 | Matthews, Luke | PCB Test and assembly doc revision |  | 14:30 | 15:30 | 1 | DOCUMENT - ADMIN
2026-02-24 | Matthews, Luke | PCB board prep for testing | 4.1 | 17:30 | 18:45 | 1.25 | ASSEMBLY
2026-02-24 | Matthews, Luke | NanoVNA calibration and antenna testing | 4.1g | 18:45 | 20:00 | 1.25 | TEST
2026-02-24 | Matthews, Luke | Power and IC power tests | 4.1c | 20:00 | 21:00 | 1 | TEST
2026-02-24 | Matthews, Luke | J-Link assembly | 4.1d | 21:00 | 22:15 | 1.25 | ASSEMBLY
2026-02-23 | Bah, Abdul | J-Link assembly | 4.1d | 21:00 | 22:45 | 1.75 | ASSEMBLY
2026-02-24 | Bah, Abdul | PCB board testing | 4.1 | 17:45 | 20:00 | 2.25 | TEST
2026-02-24 | Bah, Abdul | PCB power and IC testing/documentation | 4.1c | 20:00 | 21:00 | 1 | TEST
2026-02-24 | Bah, Abdul | J-Link assembly | 4.1d | 21:00 | 22:15 | 1.25 | ASSEMBLY
2026-02-25 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-02-25 | Matthews, Luke | J-Link to SOC testing | 4.1e | 20:30 | 21:15 | 0.75 | TEST
2026-02-25 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-02-25 | Bah, Abdul | J-Link to SOC testing | 4.1e | 20:30 | 21:15 | 0.75 | TEST
2026-02-26 | Matthews, Luke | Ki-Cad Power circuit Revisions | 4.1a | 10:00 | 11:00 | 1 | DESIGN
2026-02-26 | Matthews, Luke | Project Plan revisions |  | 11:00 | 11:15 | 0.25 | DOCUMENT - ADMIN
2026-02-26 | Matthews, Luke | J-Link Hardware troubleshooting research | 4.1 | 11:15 | 12:00 | 0.75 | RESEARCH
2026-02-26 | Matthews, Luke | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-02-27 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-27 | Matthews, Luke | Mentor Meeting |  | 13:00 | 13:30 | 0.5 | MENTOR
2026-03-02 | Matthews, Luke | J-TAG Connection research | 4.1 | 14:15 | 16:00 | 1.75 | RESEARCH
2026-03-02 | Matthews, Luke | Antenna ADS Simulation design revisions | 4.1 | 16:00 | 17:00 | 1 | DESIGN
2026-03-03 | Matthews, Luke | Lessons Learned Documentation |  | 17:15 | 18:00 | 0.75 | DOCUMENT - ADMIN
2026-03-03 | Matthews, Luke | Component replacement research | 4.1 | 18:00 | 18:30 | 0.5 | RESEARCH
2026-03-03 | Matthews, Luke | KiCad PCB Revisions | 4.1a | 18:30 | 18:45 | 0.25 | DESIGN
2026-03-03 | Matthews, Luke | Team Meeting |  | 20:00 | 20:30 | 0.5 | PLAN
2026-02-25 | Bah, Abdul | Mentor Meeting |  | 12:30 | 13:00 | 0.5 | MENTOR
2026-02-26 | Bah, Abdul | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-02-27 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-27 | Bah, Abdul | Lessons Learned Documentation |  | 14:30 | 15:30 | 1 | DOCUMENT - ADMIN
2026-02-27 | Bah, Abdul | Lessons Learned Documentation |  | 23:30 | 23:45 | 0.25 | DOCUMENT - ADMIN
2026-02-28 | Bah, Abdul | Research PCB GPIO5 |  | 21:15 | 22:30 | 1.25 | RESEARCH
2026-03-01 | Bah, Abdul | Research software and hardware integration |  | 22:30 | 23:00 | 0.5 | RESEARCH
2026-03-02 | Bah, Abdul | Research software and hardware integration |  | 10:00 | 10:30 | 0.5 | RESEARCH
2026-03-03 | Bah, Abdul | Team Meeting |  | 20:00 | 20:30 | 0.5 | PLAN
2026-03-04 | Matthews, Luke | Sponsor email |  | 14:15 | 14:30 | 0.25 | SUPPORTER
2026-03-04 | Matthews, Luke | Sponsor meeting with Russ |  | 16:00 | 17:00 | 1 | SUPPORTER
2026-03-05 | Matthews, Luke | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-03-05 | Matthews, Luke | Sponsor Slide Prep |  | 23:15 | 23:30 | 0.25 | DOCUMENT - ADMIN
2026-03-05 | Matthews, Luke | Fill the Gap |  | 23:30 | 23:45 | 0.25 | DOCUMENT - ADMIN
2026-03-06 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-06 | Matthews, Luke | Sponsor Email |  | 10:15 | 10:30 | 0.25 | SUPPORTER
2026-03-06 | Bah, Abdul | Sponsore Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-06 | Bah, Abdul | Fill the Gap |  | 18:30 | 19:00 | 0.5 | DOCUMENT - ADMIN
2026-03-05 | Bah, Abdul | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-03-06 | Matthews, Luke | KiCad Revisions | 4.1a | 16:45 | 18:00 | 1.25 | DESIGN
2026-03-07 | Matthews, Luke | PCB Assembly | 4.1 | 10:15 | 16:00 | 5.75 | ASSEMBLY
2026-03-08 | Matthews, Luke | Sponsor email | 4.1 | 13:15 | 13:30 | 0.25 | SUPPORTER
2026-03-08 | Matthews, Luke | KiCad Revisions | 4.1a | 13:30 | 14:15 | 0.75 | DESIGN
2026-03-10 | Matthews, Luke | J-Link integration attempt | 4.1d | 16:00 | 17:15 | 1.25 | ASSEMBLY
2026-03-10 | Matthews, Luke | Sponsor Email | 4.1 | 21:00 | 22:00 | 1 | SUPPORTER
2026-03-11 | Matthews, Luke | KiCad Revisions | 4.1a | 13:00 | 14:30 | 1.5 | DESIGN
2026-03-11 | Matthews, Luke | Power Supply redesign research | 4.1 | 21:00 | 22:45 | 1.75 | RESEARCH
2026-03-12 | Matthews, Luke | Inventory |  | 12:00 | 13:30 | 1.5 | PROCUREMENT
2026-03-12 | Matthews, Luke | Mentor Meeting |  | 13:30 | 15:00 | 1.5 | SUPPORTER
2026-03-12 | Matthews, Luke | LDO Testing | 4.1c | 15:00 | 15:45 | 0.75 | TEST
2026-03-07 | Bah, Abdul | PCB Assembly | 4.1 | 10:15 | 16:00 | 5.75 | ASSEMBLY
2026-03-10 | Bah, Abdul | J-Link Integration attempt | 4.1d | 16:00 | 17:15 | 1.25 | ASSEMBLY
2026-03-11 | Bah, Abdul | Power Supply research |  | 20:00 | 21:00 | 1 | RESEARCH
2026-03-12 | Bah, Abdul | Inventory |  | 12:00 | 13:30 | 1.5 | PROCUREMENT
2026-03-12 | Bah, Abdul | Sponsor Meeting |  | 13:30 | 15:00 | 1.5 | SUPPORTER
2026-03-12 | Bah, Abdul | LDO Testing | 4.1c | 15:00 | 15:45 | 0.75 | TEST
2026-03-13 | Matthews, Luke | Power circuit redesign research | 4.1 | 11:00 | 12:00 | 1 | RESEARCH
2026-03-14 | Matthews, Luke | KiCad Revisions | 4.1a | 13:00 | 16:15 | 3.25 | DESIGN
2026-03-16 | Matthews, Luke | KiCad Revisions | 4.1a | 13:00 | 16:45 | 3.75 | DESIGN
2026-03-17 | Matthews, Luke | BOM creation |  | 12:30 | 15:15 | 2.75 | DOCUMENT - ADMIN
2026-03-17 | Matthews, Luke | PRP Slide prep |  | 19:00 | 19:45 | 0.75 | DOCUMENT - ADMIN
2026-03-17 | Matthews, Luke | Sponsor Email |  | 19:45 | 20:00 | 0.25 | SUPPORTER
2026-03-16 | Bah, Abdul | PRP Slide prep |  | 23:15 | 23:45 | 0.5 | DOCUMENT - ADMIN
2026-03-17 | Bah, Abdul | PRP Slide prep |  | 21:30 | 23:00 | 1.5 | DOCUMENT - ADMIN
2026-03-17 | Bah, Abdul | Inventory |  | 23:00 | 23:30 | 0.5 | PROCUREMENT
2026-03-18 | Bah, Abdul | PRP Slide prep |  | 18:00 | 18:45 | 0.75 | DOCUMENT - ADMIN
2026-03-18 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-03-18 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-03-18 | Matthews, Luke | Sponsor Email |  | 19:00 | 19:30 | 0.5 | SUPPORTER
2026-03-18 | Matthews, Luke | Team Meeting |  | 20:15 | 21:45 | 1.5 | PLAN
2026-02-23 | Le, Kenneth | Learning Node-RED Custom Login Creation | 4.4d | 19:00 | 21:00 | 2 | RESEARCH
2026-02-24 | Le, Kenneth | Login Creation | 4.4d | 10:00 | 12:00 | 2 | PROGRAMMING/ SOFTWARE
2026-02-25 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-02-25 | Le, Kenneth | Timeout Session Creation | 4.4d | 20:30 | 22:30 | 2 | PROGRAMMING/ SOFTWARE
2026-02-26 | Le, Kenneth | Login Bug Fixes | 4.4d | 12:00 | 14:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-02-27 | Le, Kenneth | Login Documentation | 4.4d | 17:00 | 19:00 | 2 | DOCUMENT - ADMIN
2026-02-27 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-03-02 | Le, Kenneth | Timeout Session Bug Fix | 4.4d | 21:00 | 23:00 | 2 | PROGRAMMING/ SOFTWARE
2026-03-03 | Le, Kenneth | Raspberry Pi 4 Gateway Setup | 4.4e | 10:00 | 14:00 | 4 | DESIGN
2026-03-03 | Le, Kenneth | Team Meeting |  | 20:00 | 20:30 | 0.5 | PLAN
2026-03-04 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-04 | Le, Kenneth | Gateway to UI Integration | 4.e | 16:00 | 18:00 | 2 | PROGRAMMING/ SOFTWARE
2026-03-05 | Le, Kenneth | Gateway to UI Integration | 4.e | 20:00 | 23:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-06 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-06 | Le, Kenneth | Gateway Documentation | 4.e | 9:00 | 12:00 | 3 | DOCUMENT - ADMIN
2026-03-16 | Le, Kenneth | UI for Motion Sensor Bug Fix | 4.a | 10:00 | 11:00 | 1 | PROGRAMMING/ SOFTWARE
2026-03-17 | Le, Kenneth | UI for Doorbell | 4.b | 17:00 | 21:00 | 4 | PROGRAMMING/ SOFTWARE
2026-03-17 | Le, Kenneth | PRP Slide prep |  | 21:00 | 23:00 | 2 | DOCUMENT - ADMIN
2026-03-18 | Le, Kenneth | UI for Speaker | 4.c | 21:00 | 22:00 | 1 | PROGRAMMING/ SOFTWARE
2026-03-19 | Le, Kenneth | PRP Presentation at Qorvo + Tour |  | 9:45 | 15:15 | 5.5 | SUPPORTER
2026-03-19 | Matthews, Luke | PRP Presentation and tour |  | 9:45 | 15:15 | 5.5 | SUPPORTER
2026-03-18 | Bah, Abdul | Team Meeting |  | 20:45 | 21:45 | 1 | PLAN
2026-03-19 | Bah, Abdul | PRP Presentation and Tour |  | 9:45 | 15:15 | 5.5 | SUPPORTER
2026-03-20 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 9:30 | 1.5 | SUPPORTER
2026-02-25 | Hernandez, Alberto | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-02-26 | Hernandez, Alberto | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-02-27 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-23 | Hernandez, Alberto | Thread Dubugging | 4.2d | 9:00 | 11:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-02-26 | Hernandez, Alberto | Doorbell Firmware | 4.2a | 9:00 | 11:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-03-02 | Hernandez, Alberto | Motion Snesor Firmware | 4.2b | 9:30 | 11:45 | 2.25 | PROGRAMMING/ SOFTWARE
2026-03-04 | Hernandez, Alberto | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-03 | Hernandez, Alberto | Team Meeting |  | 20:00 | 20:30 | 0.5 | PLAN
2026-03-04 | Hernandez, Alberto | JTag research |  | 10:00 | 11:00 | 1 | RESEARCH
2026-03-05 | Hernandez, Alberto | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-03-05 | Hernandez, Alberto | Gateway setup | 4.3 | 20:00 | 21:00 | 1 | PROGRAMMING/ SOFTWARE
2026-03-06 | Hernandez, Alberto | Sponsor meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-03-08 | Hernandez, Alberto | Gateway Setup | 4.3 | 20:00 | 23:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-09 | Hernandez, Alberto | Gateway Pi Setup | 4.3a | 11:00 | 15:00 | 4 | PROGRAMMING/ SOFTWARE
2026-03-09 | Hernandez, Alberto | Gateway Dongle Setup | 4.3b | 19:00 | 22:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-10 | Hernandez, Alberto | Jlink integration |  | 16:00 | 17:15 | 1.25 | ASSEMBLY
2026-03-16 | Hernandez, Alberto | Full software Integration |  | 8:00 | 11:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-16 | Hernandez, Alberto | Full software Integration |  | 16:00 | 19:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-18 | Hernandez, Alberto | Mentor Meeting |  | 8:15 | 8:45 | 0.5
2026-03-17 | Hernandez, Alberto | PRP Slide prep |  | 19:00 | 20:00 | 1 | DOCUMENT - ADMIN
2026-03-18 | Hernandez, Alberto | Router Pi Connecteion | 4.3 | 15:00 | 20:00 | 5 | PROGRAMMING/ SOFTWARE
2026-03-18 | Hernandez, Alberto | Team Meeting |  | 20:15 | 21:30 | 1.25 | PLAN
2026-03-18 | Hernandez, Alberto | DK, Gateway, Router, UI, demo | 4.3/4.2 | 22:00 | 23:45 | 1.75 | PROGRAMMING/ SOFTWARE
2026-03-19 | Hernandez, Alberto | DK, Gateway, Router, UI, demo | 4.3/4.2 | 0:00 | 3:30 | 3.5 | PROGRAMMING/ SOFTWARE
2026-03-19 | Hernandez, Alberto | PRP Presentation and Tour |  | 9:45 | 15:15 | 5.5 | SUPPORTER
2026-02-23 | Hartman, Ethan | SD2 Lecture |  | 8:00 | 9:45 | 1.75 | PLAN
2026-02-25 | Hartman, Ethan | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-02-26 | Hartman, Ethan | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-02-27 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-02-27 | Hartman, Ethan | Expo Requirements Form |  | 14:00 | 14:30 | 0.5 | DOCUMENT - TECH
2026-03-04 | Hartman, Ethan | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-03-05 | Hartman, Ethan | Budget Breakdown |  | 13:00 | 16:00 | 3 | DOCUMENT - ADMIN
2026-03-05 | Hartman, Ethan | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-03-06 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-06 | Hartman, Ethan | Fill the Gap |  | 13:00 | 13:30 | 0.5 | DOCUMENT - TECH
2026-03-07 | Hartman, Ethan | PCB Assembly with Luke and Abdul | 4.1 | 10:30 | 14:30 | 4 | ASSEMBLY
2026-03-08 | Hartman, Ethan | PRP Slide prep |  | 14:00 | 16:00 | 2 | DOCUMENT - TECH
2026-03-13 | Hartman, Ethan | Battery housing design | 3.2 | 15:00 | 18:00 | 3 | DESIGN
2026-03-15 | Hartman, Ethan | Battery Housing Design | 3.2 | 14:00 | 17:00 | 3 | DESIGN
2026-03-16 | Hartman, Ethan | PRP Slide prep |  | 20:00 | 23:00 | 3 | DOCUMENT - TECH
2026-03-17 | Hartman, Ethan | Battery Housing Design | 3.2 | 10:00 | 14:00 | 4 | DESIGN
2026-03-17 | Hartman, Ethan | 3D Printing Prep | 4.6 | 14:00 | 14:30 | 0.5 | ASSEMBLY
2026-03-17 | Hartman, Ethan | Budget Breakdown |  | 14:30 | 16:00 | 1.5 | DOCUMENT - TECH
2026-03-18 | Hartman, Ethan | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-03-18 | Hartman, Ethan | Enclosure Assembly | 4.7 | 12:00 | 13:00 | 1 | ASSEMBLY
2026-03-18 | Hartman, Ethan | PRP Slide prep |  | 13:00 | 14:30 | 1.5 | DOCUMENT - TECH
2026-03-18 | Hartman, Ethan | Team Meeting |  | 20:30 | 21:45 | 1.25 | PLAN
2026-03-18 | Hartman, Ethan | PRP Supplemental Material Prep |  | 22:00 | 23:00 | 1 | DOCUMENT - ADMIN
2026-03-19 | Hartman, Ethan | PRP Presentation and Tour |  | 9:45 | 15:15 | 5.5 | SUPPORTER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 4
Team Member Name | Total Timesheet Hours | Timesheet 4 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Bah, Abdul | 22.5 | QORVO_RADIO2 | ANALYSIS | 0
Hartman, Ethan | 18.75 |  | ASSEMBLY | 0
Hernandez, Alberto | 39.5 |  | DESIGN | 10.25
Le, Kenneth | 31.6667 |  | DOCUMENT - ADMIN | 57.75
Matthews, Luke | 27.5 |  | DOCUMENT - TECH | 1.25
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 4.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 17.8333
| 0 |  | PROCUREMENT | 2.25
|  |  | PROGRAMMING/ SOFTWARE | 22.5
|  |  | RESEARCH | 13
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 5.0833
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2026-03-20 | Matthews, Luke | KiCad revisions and battery charger research | 4.1p | 16:00 | 17:00 | 1 | DESIGN
2026-03-23 | Matthews, Luke | KiCad revisions | 4.1p | 17:00 | 18:00 | 1 | DESIGN
2026-03-24 | Matthews, Luke | KiCad Revisions | 4.1p | 10:00 | 11:00 | 1 | DESIGN
2026-03-24 | Matthews, Luke | Sponsor meeting for board review | 4.1p | 12:30 | 15:30 | 3 | SUPPORTER
2026-03-24 | Matthews, Luke | Mentor Meeting slide prep |  | 18:15 | 18:45 | 0.5 | DOCUMENT - ADMIN
2026-03-24 | Matthews, Luke | KiCad Revisions | 4.1p | 18:45 | 20:00 | 1.25 | DESIGN
2026-03-23 | Hernandez, Alberto | Thread Mesh Debugging | 4.2d | 9:00 | 11:45 | 2.75 | PROGRAMMING/ SOFTWARE
2026-03-24 | Hernandez, Alberto | Serial Comm Verification |  | 17:45 | 20:15 | 2.5 | RESEARCH
2026-03-24 | Hernandez, Alberto | Mentor Meeting slide prep |  | 21:45 | 22:15 | 0.5 | DOCUMENT - ADMIN
2026-03-25 | Matthews, Luke | Mentor Meeting slide prep |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-25 | Matthews, Luke | PR Prep |  | 21:30 | 23:00 | 1.5 | DOCUMENT - ADMIN
2026-03-26 | Matthews, Luke | PR Prep |  | 10:00 | 11:30 | 1.5 | DOCUMENT - ADMIN
2026-03-26 | Matthews, Luke | Team Meeting |  | 19:00 | 19:15 | 0.25 | PLAN
2026-03-27 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-27 | Matthews, Luke | OSH park and stencil quote |  | 8:30 | 9:00 | 0.5 | PROCUREMENT
2026-03-27 | Matthews, Luke | PR Revisions |  | 10:30 | 11:30 | 1 | DOCUMENT - ADMIN
2026-03-30 | Matthews, Luke | Progress Report |  | 15:00 | 16:15 | 1.25 | DOCUMENT - ADMIN
2026-04-01 | Matthews, Luke | Mentor Slide creation |  | 0:00 | 0:30 | 0.5 | DOCUMENT - ADMIN
2026-04-01 | Matthews, Luke | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-04-02 | Matthews, Luke | Operation Manual Doc |  | 10:00 | 12:00 | 2 | DOCUMENT - ADMIN
2026-04-02 | Matthews, Luke | operation Manual Doc |  | 17:15 | 18:00 | 0.75 | DOCUMENT - ADMIN
2026-04-02 | Matthews, Luke | Team Meeting |  | 18:45 | 19:30 | 0.75 | PLAN
2026-04-02 | Matthews, Luke | Sponsor Slide prep |  | 22:00 | 22:15 | 0.25 | DOCUMENT - ADMIN
2026-04-03 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-04-03 | Matthews, Luke | Expo Poster and Operation Manual |  | 11:45 | 13:15 | 1.5 | DOCUMENT - ADMIN
2026-04-07 | Matthews, Luke | Email corrospondence with Mr. Keys |  | 13:15 | 13:30 | 0.25 | PROCUREMENT
2026-04-08 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-08 | Matthews, Luke | Expo Poster prep |  | 12:00 | 12:45 | 0.75 | DOCUMENT - ADMIN
2026-04-09 | Matthews, Luke | Battery life recalculations |  | 11:00 | 13:00 | 2 | DESIGN
2026-03-23 | Le, Kenneth | MQTT Research |  | 12:00 | 14:00 | 2 | RESEARCH
2026-03-24 | Le, Kenneth | MQTT Research |  | 13:00 | 15:00 | 2 | RESEARCH
2026-03-24 | Le, Kenneth | Mentor Meeting slide prep |  | 0:00 | 0:15 | 0.25 | DOCUMENT - ADMIN
2026-03-25 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-25 | Le, Kenneth | Setup Instructions |  | 19:00 | 21:00 | 2 | DOCUMENT - ADMIN
2026-03-26 | Le, Kenneth | Team Meeting |  | 7:00 | 7:20 | 0.33333 | PLAN
2026-03-26 | Le, Kenneth | Speaker Development | 4.4c | 11:00 | 13:00 | 2 | PROGRAMMING/ SOFTWARE
2026-03-27 | Le, Kenneth | Speaker Development | 4.4c | 13:00 | 15:00 | 2 | PROGRAMMING/ SOFTWARE
2026-03-30 | Le, Kenneth | Progress Report |  | 19:00 | 21:00 | 2 | DOCUMENT - ADMIN
2026-03-31 | Le, Kenneth | Progress Report |  | 20:00 | 23:00 | 3 | DOCUMENT - ADMIN
2026-04-01 | Le, Kenneth | Updated Project Plan |  | 0:00 | 2:00 | 2 | DOCUMENT - ADMIN
2026-04-01 | Le, Kenneth | Mentor Slide creation |  | 1:00 | 1:30 | 0.5 | DOCUMENT - ADMIN
2026-04-02 | Le, Kenneth | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-03 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:20 | 0.33333 | SUPPORTER
2026-04-03 | Le, Kenneth | Updated Project Plan |  | 13:00 | 15:00 | 2 | DOCUMENT - ADMIN
2026-04-06 | Le, Kenneth | Expo Poster |  | 13:00 | 16:00 | 3 | DOCUMENT - ADMIN
2026-04-07 | Le, Kenneth | Expo Poster |  | 14:00 | 15:30 | 1.5 | DOCUMENT - ADMIN
2026-04-07 | Le, Kenneth | Mentor Meeting slide prep |  | 9:00 | 12:00 | 3 | DOCUMENT - ADMIN
2026-04-08 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-08 | Le, Kenneth | Expo Poster |  | 1:00 | 3:00 | 2 | DOCUMENT - ADMIN
2026-04-09 | Le, Kenneth | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-03-21 | Bah, Abdul | Assembly Excel Documentation |  | 13:00 | 14:00 | 1 | DOCUMENT - ADMIN
2026-03-22 | Bah, Abdul | Assembly Excel Documentation |  | 21:00 | 22:00 | 1 | DOCUMENT - ADMIN
2026-03-24 | Bah, Abdul | Testing Excel Documentation |  | 22:00 | 23:00 | 1 | DOCUMENT - ADMIN
2026-03-25 | Bah, Abdul | Testing Excel Documentation |  | 21:30 | 22:00 | 0.5 | DOCUMENT - ADMIN
2026-03-25 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-25 | Bah, Abdul | Testing Excel Documentation |  | 22:00 | 22:30 | 0.5 | DOCUMENT - ADMIN
2026-03-27 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-30 | Bah, Abdul | Progress Report |  | 16:30 | 17:30 | 1 | DOCUMENT - ADMIN
2026-04-01 | Bah, Abdul | Progress Report |  | 20:00 | 21:00 | 1 | DOCUMENT - ADMIN
2026-04-02 | Bah, Abdul | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-03 | Bah, Abdul | Progress Report |  | 13:30 | 14:30 | 1 | DOCUMENT - ADMIN
2026-03-27 | Bah, Abdul | ISL Purchasing Office |  | 12:00 | 12:15 | 0.25 | PLAN
2026-04-05 | Bah, Abdul | Project Video Planning |  | 10:00 | 12:00 | 2 | PLAN
2026-04-06 | Bah, Abdul | Project Video Planning |  | 8:00 | 10:00 | 2 | PLAN
2026-04-07 | Bah, Abdul | Project Video Planning and Outline |  | 12:30 | 14:00 | 1.5 | PLAN
2026-04-08 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-09 | Bah, Abdul | Project Video Script Outline |  | 0:30 | 2:00 | 1.5 | PLAN
2026-04-09 | Bah, Abdul | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-08 | Bah, Abdul | KiCAD Netlist |  | 0:00 | 2:00 | 2 | DOCUMENT - ADMIN
2026-04-10 | Matthews, Luke | Inventory |  | 11:00 | 12:45 | 1.75
2026-03-25 | Hernandez, Alberto | Mentor meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-03-25 | Hernandez, Alberto | Thread Mesh Debugging | 4.2d | 15:00 | 18:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-26 | Hernandez, Alberto | Thread Mesh Debugging | 4.2d | 9:00 | 12:00 | 3 | PROGRAMMING/ SOFTWARE
2026-03-26 | Hernandez, Alberto | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-03-26 | Hernandez, Alberto | Sponsor Meeting Prep |  | 21:00 | 21:30 | 0.5 | DOCUMENT - ADMIN
2026-03-27 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-03-30 | Hernandez, Alberto | Gateway Documentation Creation |  | 9:00 | 11:30 | 2.5 | DOCUMENT - ADMIN
2026-03-30 | Hernandez, Alberto | Application Documentation Creation |  | 15:00 | 17:00 | 2 | DOCUMENT - ADMIN
2026-03-31 | Hernandez, Alberto | Node Red Documentation |  | 9:00 | 11:45 | 2.75 | DOCUMENT - ADMIN
2026-03-31 | Hernandez, Alberto | md files for doorbell and motion sensor |  | 14:30 | 17:15 | 2.75 | DOCUMENT - ADMIN
2026-03-31 | Hernandez, Alberto | Motion Detecto Full Integration | 4.2b | 20:00 | 22:00 | 2 | PROGRAMMING/ SOFTWARE
2026-03-31 | Hernandez, Alberto | Mentor Meeting Slide prep |  | 22:00 | 22:30 | 0.5 | DOCUMENT - ADMIN
2026-04-01 | Hernandez, Alberto | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-04-01 | Hernandez, Alberto | Github Repo Organizing |  | 14:30 | 16:30 | 2 | PROGRAMMING/ SOFTWARE
2026-04-02 | Hernandez, Alberto | Github Repo Organizing |  | 9:00 | 10:45 | 1.75 | PROGRAMMING/ SOFTWARE
2026-03-31 | Hernandez, Alberto | Progress Report |  | 17:30 | 19:00 | 1.5 | DOCUMENT - ADMIN
2026-04-02 | Hernandez, Alberto | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-09 | Hernandez, Alberto | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-07 | Hernandez, Alberto | Poster Creation |  | 14:30 | 16:00 | 1.5 | DOCUMENT - ADMIN
2026-04-08 | Hernandez, Alberto | Poster Edits |  | 16:30 | 17:15 | 0.75 | DOCUMENT - ADMIN
2026-04-06 | Hernandez, Alberto | Demo Creations for Video | 4.2 | 9:00 | 11:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-04-06 | Hernandez, Alberto | Integrated Doorbell with UI | 4.2 | 14:00 | 15:30 | 1.5 | PROGRAMMING/ SOFTWARE
2026-04-07 | Hernandez, Alberto | Mentor Meeting Slide prep |  | 20:00 | 20:15 | 0.25 | DOCUMENT - ADMIN
2026-04-08 | Hernandez, Alberto | Mentor meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-10 | Bah, Abdul | Inventory |  | 11:00 | 12:45 | 1.75
2026-04-10 | Bah, Abdul | BOM and Inventory Check |  | 12:45 | 14:45 | 2
2026-04-10 | Bah, Abdul | KiCAD Netlist |  | 10:00 | 10:30 | 0.5 | DOCUMENT - ADMIN
2026-04-10 | Matthews, Luke | Battery Charger |  | 13:00 | 14:30 | 1.5 | RESEARCH
2026-03-22 | Hartman, Ethan | Enclosure CAD updates | 3.2 | 14:00 | 18:00 | 4 | DESIGN
2026-03-24 | Hartman, Ethan | Mentor Meeting Slide prep |  | 22:00 | 22:15 | 0.25 | DOCUMENT - TECH
2026-03-25 | Hartman, Ethan | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-03-26 | Hartman, Ethan | Team Meeting |  | 19:00 | 19:15 | 0.25 | PLAN
2026-03-26 | Hartman, Ethan | Sponsor Meeting Slide Prep |  | 20:00 | 20:30 | 0.5 | DOCUMENT - TECH
2026-03-27 | Hartman, Ethan | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-03-27 | Hartman, Ethan | PR Form Chack and Submittal |  | 11:30 | 12:00 | 0.5 | PROCUREMENT
2026-03-29 | Hartman, Ethan | Video Research |  | 13:00 | 16:00 | 3 | RESEARCH
2026-03-31 | Hartman, Ethan | Mentor Meeting Slide prep |  | 21:00 | 21:15 | 0.25 | DOCUMENT - TECH
2026-04-01 | Hartman, Ethan | Mentor Meeting |  | 8:00 | 8:15 | 0.25 | MENTOR
2026-04-02 | Hartman, Ethan | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-05 | Hartman, Ethan | Capcut Research |  | 15:00 | 17:00 | 2 | RESEARCH
2026-04-07 | Hartman, Ethan | Mentor Meeting Slide prep |  | 19:00 | 19:15 | 0.25 | DOCUMENT - TECH
2026-04-08 | Hartman, Ethan | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-08 | Hartman, Ethan | Video Script Outline |  | 20:00 | 22:00 | 2 | PLAN
2026-04-09 | Hartman, Ethan | Purchase Pickup |  | 14:30 | 15:30 | 1 | PROCUREMENT
2026-04-09 | Hartman, Ethan | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2026-04-09 | Hartman, Ethan | Video Script Outline |  | 21:00 | 23:30 | 2.5 | PLAN
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 5
Team Member Name | Total Timesheet Hours | Timesheet 5 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Bah, Abdul | 24.75 | QORVO_RADIO2 | ANALYSIS | 0
Hartman, Ethan | 0 |  | ASSEMBLY | 19
Hernandez, Alberto | 38.25 |  | DESIGN | 0
Le, Kenneth | 31.25 |  | DOCUMENT - ADMIN | 30
Matthews, Luke | 31.75 |  | DOCUMENT - TECH | 0
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 3.25
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 12.75
| 0 |  | PROCUREMENT | 0.5
|  |  | PROGRAMMING/ SOFTWARE | 30
|  |  | RESEARCH | 3.5
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 24
|  | remove example team and timesheet entry | TEST | 3
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2026-04-14 | Matthews, Luke | Mentor Slide Prep |  | 18:30 | 19:00 | 0.5 | DOCUMENT - ADMIN
2026-04-15 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-15 | Matthews, Luke | Board Pickup from ISL |  | 14:45 | 15:00 | 0.25 | PROCUREMENT
2026-04-15 | Matthews, Luke | Board Assembly | 4.1 | 20:29 | 23:59 | 3.5 | ASSEMBLY
2026-04-16 | Matthews, Luke | Team meeting and SOC testing | 4.1 | 19:00 | 20:15 | 1.25 | PLAN
2026-04-16 | Matthews, Luke | Sponsor slide prep |  | 21:00 | 21:15 | 0.25 | DOCUMENT - ADMIN
2026-04-16 | Matthews, Luke | Poster revisions |  | 21:15 | 21:30 | 0.25 | DOCUMENT - ADMIN
2026-04-17 | Matthews, Luke | Sponsor Meeting |  | 8:15 | 8:30 | 0.25 | SUPPORTER
2026-04-17 | Matthews, Luke | J-Tag Programming Solution Reserach |  | 18:00 | 19:15 | 1.25 | RESEARCH
2026-04-17 | Matthews, Luke | Video voice recording |  | 23:00 | 23:15 | 0.25 | DOCUMENT - ADMIN
2026-04-19 | Matthews, Luke | Video recording |  | 12:15 | 13:45 | 1.5 | DOCUMENT - ADMIN
2026-04-20 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-04-21 | Matthews, Luke | PCB Assembly | 4.1 | 17:30 | 20:30 | 3 | ASSEMBLY
2026-04-22 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-23 | Matthews, Luke | Team meeting and dev kit PCB intergration | 4.1 | 19:00 | 22:00 | 3 | TEST
2026-04-24 | Matthews, Luke | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-04-14 | Bah, Abdul | Script Outline |  | 15:00 | 16:00 | 1 | PLAN
2026-04-14 | Bah, Abdul | Meeting with Ethan |  | 16:00 | 16:45 | 0.75 | PLAN
2026-04-15 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-15 | Bah, Abdul | Board Assembly | 4.1 | 20:29 | 23:59 | 3.5 | ASSEMBLY
2026-04-16 | Bah, Abdul | Team Meeting |  | 19:00 | 20:15 | 1.25 | PLAN
2026-04-17 | Bah, Abdul | Sponsor Meeting |  | 8:15 | 8:30 | 0.25 | SUPPORTER
2026-04-19 | Bah, Abdul | PCB Testing and Video Recording |  | 12:15 | 13:45 | 1.5 | DOCUMENT - ADMIN
2026-04-19 | Bah, Abdul | Video Voice Recording |  | 10:00 | 10:15 | 0.25 | DOCUMENT - ADMIN
2026-04-19 | Bah, Abdul | Video Editing |  | 13:45 | 15:30 | 1.75 | DOCUMENT - ADMIN
2026-04-20 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-04-21 | Bah, Abdul | PCB Assembly |  | 18:00 | 20:30 | 2.5 | ASSEMBLY
2026-04-22 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-22 | Bah, Abdul | Meeting with Ethan |  | 20:30 | 20:45 | 0.25 | PLAN
2026-04-23 | Bah, Abdul | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-04-23 | Bah, Abdul | Software to Hardware integration and Video |  | 20:00 | 22:00 | 2 | DOCUMENT - ADMIN
2026-04-24 | Bah, Abdul | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-04-25 | Matthews, Luke | PCB Assembly | 4.1 | 12:00 | 14:15 | 2.25 | ASSEMBLY
2026-04-22 | Bah, Abdul | ISL Purchase Pickup |  | 12:00 | 12:15 | 0.25 | PROCUREMENT
2026-04-25 | Bah, Abdul | PCB Assembly |  | 12:00 | 14:15 | 2.25 | ASSEMBLY
2026-04-26 | Matthews, Luke | Final Report |  | 12:00 | 14:00 | 2 | DOCUMENT - ADMIN
2026-04-26 | Matthews, Luke | SPI Programming Research |  | 20:00 | 21:00 | 1 | RESEARCH
2026-04-27 | Matthews, Luke | Final Report |  | 15:00 | 16:45 | 1.75 | DOCUMENT - ADMIN
2026-04-28 | Matthews, Luke | final Assembly | 4.1 | 17:30 | 18:30 | 1 | ASSEMBLY
2026-04-28 | Bah, Abdul | Final Assembly | 4.1 | 17:30 | 18:30 | 1 | ASSEMBLY
2026-04-28 | Bah, Abdul | Final Report |  | 21:59 | 23:59 | 2 | DOCUMENT - ADMIN
2026-04-29 | Bah, Abdul | Final Report |  | 0:00 | 1:00 | 1 | DOCUMENT - ADMIN
2026-04-30 | Matthews, Luke | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-29 | Bah, Abdul | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-29 | Bah, Abdul | Final Report |  | 8:30 | 9:00 | 0.5 | DOCUMENT - ADMIN
2026-04-13 | Le, Kenneth | Login Screen bug fixes |  | 21:00 | 23:00 | 2 | PROGRAMMING/ SOFTWARE
2026-04-14 | Le, Kenneth | Timer Bug Fixes |  | 12:00 | 15:00 | 3 | PROGRAMMING/ SOFTWARE
2026-04-15 | Le, Kenneth | Mentor Slide Prep |  | 1:00 | 1:30 | 0.5 | DOCUMENT - ADMIN
2026-04-15 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-16 | Le, Kenneth | Timer Bug Fixes |  | 17:00 | 21:00 | 4 | PROGRAMMING/ SOFTWARE
2026-04-16 | Le, Kenneth | Team meeting |  | 19:00 | 20:15 | 1.25 | PLAN
2026-04-17 | Le, Kenneth | Poster Revisions |  | 23:00 | 23:30 | 0.5 | DOCUMENT - ADMIN
2026-04-17 | Le, Kenneth | Video recording of UI and voiceover |  | 1:00 | 2:00 | 1 | DOCUMENT - ADMIN
2026-04-20 | Le, Kenneth | Info Tab Creation |  | 14:00 | 17:00 | 3 | PROGRAMMING/ SOFTWARE
2026-04-20 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-04-21 | Le, Kenneth | Info Tab Finalized |  | 15:30 | 17:00 | 1.5 | PROGRAMMING/ SOFTWARE
2026-04-21 | Le, Kenneth | Mentor Slide Prep |  | 23:00 | 23:30 | 0.5 | DOCUMENT - ADMIN
2026-04-22 | Le, Kenneth | Mentor Meeting |  | 8:15 | 8:45 | 0.5 | MENTOR
2026-04-23 | Le, Kenneth | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2026-04-24 | Le, Kenneth | Fix audio file & upload to Github |  | 13:00 | 14:00 | 1 | PROGRAMMING/ SOFTWARE
2026-04-24 | Le, Kenneth | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-04-27 | Le, Kenneth | File Corruption Fix |  | 11:00 | 11:30 | 0.5 | PROGRAMMING/ SOFTWARE
2026-04-28 | Le, Kenneth | Final Report |  | 17:00 | 19:00 | 2 | DOCUMENT - ADMIN
2026-04-29 | Le, Kenneth | Final Report |  | 13:00 | 14:00 | 1 | DOCUMENT - ADMIN
2026-04-30 | Le, Kenneth | Team Meeting |  | 15:30 | 16:00 | 0.5 | PLAN
2026-05-01 | Le, Kenneth | Senior Design Expo |  | 9:00 | 15:30 | 6.5 | SUPPORTER
2026-05-01 | Matthews, Luke | Senior Design Expo and clean up |  | 9:15 | 16:00 | 6.75 | SUPPORTER
2026-05-01 | Hernandez, Alberto | Senior Design Expo and clean up |  | 9:15 | 16:00 | 6.75 | SUPPORTER
2026-04-24 | Hernandez, Alberto | Sponsor Meeeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-04-13 | Hernandez, Alberto | Created Doorbell demo for video |  | 9:30 | 11:30 | 2 | PROGRAMMING/ SOFTWARE
2026-04-14 | Hernandez, Alberto | Connected Doorbell to Gateway and UI |  | 10:00 | 13:00 | 3 | PROGRAMMING/ SOFTWARE
2026-04-15 | Hernandez, Alberto | Mentor Meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-04-16 | Hernandez, Alberto | Motion Sensor Demo |  | 16:00 | 18:30 | 2.5 | PROGRAMMING/ SOFTWARE
2026-04-16 | Hernandez, Alberto | Team meeting and SOC testing |  | 19:00 | 20:15 | 1.25 | PLAN
2026-04-17 | Hernandez, Alberto | Sponsor Meeting |  | 8:00 | 8:15 | 0.25 | SUPPORTER
2026-04-17 | Hernandez, Alberto | Demo Setup and recording |  | 21:00 | 23:00 | 2 | DOCUMENT - ADMIN
2026-04-20 | Hernandez, Alberto | Sponsor meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2026-04-20 | Hernandez, Alberto | Created Speaker demo for testing |  | 9:30 | 11:30 | 2 | PROGRAMMING/ SOFTWARE
2026-04-21 | Hernandez, Alberto | Created Mic demo for testing |  | 9:30 | 12:30 | 3 | PROGRAMMING/ SOFTWARE
2026-04-22 | Hernandez, Alberto | Mentor meeting |  | 8:15 | 8:30 | 0.25 | SUPPORTER
2026-04-23 | Hernandez, Alberto | SDK User guide |  | 11:00 | 12:15 | 1.25 | DOCUMENT - ADMIN
2026-04-23 | Hernandez, Alberto | SDK User guide |  | 16:00 | 18:30 | 2.5 | DOCUMENT - ADMIN
2026-04-23 | Hernandez, Alberto | Software to Hardware integration and Video |  | 20:00 | 22:00 | 2 | PLAN
2026-04-22 | Hernandez, Alberto | Devboard schematic research |  | 17:00 | 18:15 | 1.25 | RESEARCH
2026-04-15 | Hernandez, Alberto | Putting Drive on github |  | 18:00 | 19:00 | 1 | PROGRAMMING/ SOFTWARE
2026-04-28 | Hernandez, Alberto | Final report |  | 20:00 | 22:00 | 2 | DOCUMENT - ADMIN
2026-04-29 | Hernandez, Alberto | Final report |  | 7:15 | 8:30 | 1.25 | DOCUMENT - ADMIN
2026-04-29 | Hernandez, Alberto | Mentor meeting |  | 8:15 | 8:30 | 0.25 | MENTOR
2026-05-01 | Hernandez, Alberto | Peer Evaluations/Survey |  | 16:00 | 17:15 | 1.25 | PLAN
2026-05-01 | Hernandez, Alberto | Adding Drive updated to Repo |  | 17:15 | 18:45 | 1.5 | PROGRAMMING/ SOFTWARE
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Control Table
In Alpha Order by last name
Team Members Last,First | Work Breakdown Structure Elements
Hartman, Ethan |  | Set Date range in Data Validation
Bah, Abdul | ANALYSIS | 08/18/2025 - 05/12/2026
Le, Kenneth | ASSEMBLY
Hernandez, Alberto | DESIGN
Matthews, Luke | DOCUMENT - ADMIN
DOCUMENT - TECH
FABRICATION
MENTOR
OUTREACH
PLAN
PROCUREMENT
PROGRAMMING/ SOFTWARE
RESEARCH
SOW
SUPPORTER
TEST

## Instructions
Instructions for completing the Timesheet
Timesheet is designed to work in Excel, download it in Excel, submit it in Excel. Some features and calculations do not work in Google Sheets.
Set up
on Timesheet Dashboard:
List team members Banner names in alphabetical order by last name starting in block A4
Put team name in block L2
Do not modify any other blocks on Timesheet Dashboard worksheet
Adjust Data Validation on each timesheet:
Highlight Cell A22-A200 on the first timesheet
Go to Data in the Menu
Select ^ next to Data Validation
In the dropdown menu, select Data Validation
In the Popup screen, set the validation criteria, select Date and set the dates to suit your semester.
Check the box "Apply these changes to all other cells with the same setting"
Click OK
Repeat on each Timesheet.
For the first module, go to Timesheet 1:
Lines 1-21 are autofilled, do not modify.
Beginning on line 22, use dropdown menues to detail work done on the project by each student, each day. Use the drop down menues where available. Catagorize each task as a Work Breakdown Structure element from the drop down menu.
Overwrite the example on line 22 line with your data.
Continue for every team members tasks during that Timesheet period.
Class lectures and quizzes are not logged as project time.
Each subsequent timesheet should use the same base document and move to the next tab.
To submit: | Download as an Excel document and name appropriately
Download the Timesheet as an Excel (.xlsx) document, label the document with your Team name and assignment (Example: CLOISTER_FILLER_Timesheet1) and submit to Canvas.
Do not modify another student's submitted time. If you have concerns about falsification of the timesheet, contact your mentor or instructor of record.
WBS Element | DESCRIPTION
SUPPORTER | Meeting with project supporter, including Kick-Off Breakfast and plant visits for general orientation. Visits to facility with specific research or design purposes should not be included.
MENTOR | Meetings with project mentor or grading instructor. If meeting is with both mentor and supporter, use 'Supporter' code.
SOW | Time spend preparing and modifying the statement of work and requirements. This includes both initial prepration and subsequent modifications.
PLAN | Project planning includes both the preparation of the original plan and its maintenance. Also include meeting time spend organizing and planning tasks. Results of these meetings should be reflected in a Project Plan update.
RESEARCH | Technical investigation of a general nature necessary to understtand the project including library searches and reading, but does not include actual analysis carried out in support of a design. Finding fron time spent researching should be documented in the Google drive.
ANALYSIS | Analytical support of the design includes time spent in activities such as calculations, FEA analysis, circuit simulations, etc.
PROGRAMMING/ SOFTWARE | code, programming, algorithms, software architectures, or any artifact having to do with software
DESIGN | Design applies to both the creation of candidate designs during the conceptual phase and subsequent development of the selected alternative. Time spent creating ciruit diagrams, models and drawings can appear here or as part of technical documentation depending on the nature of the work.
DOCUMENT - ADMIN | Administrative documentation, such as timesheet preparation, design review preparation, and document preparation.
DOCUMENT - TECHNICAL | Design documentation can include drawings, circuit diagrams and documentation of analytical work carried out in support of the project when it is not a technically creative process. Some judgement should be applied in choosing documentation or design as a WBS category. This distinction should be consistent with the WBS and task description in the project plan.
PROCUREMENT | Preparation of procurement documents, negotiating with suppliers, ordering and picking up parts used in the project. Discussions with suppliers preliminary to design decisions are either research or design activites.
FABRICATION | Machining parts or circuits for the project.
ASSEMBLY | Assembly of the project
TEST | Testing the project and analyzing the test results.
OUTREACH | Time spent using the Senior Design program to promote STEM education or awareness in others.