## Timesheet Dashboard
Timesheet Dashboard for: |  |  | QORVO_RADIO2
Download in Excel
Fill in Team Name and Team Members Names on this page only
Team Member Name | Timesheet 1 | Timesheet 2 | Timesheet 3 | Timesheet 4 | Timesheet 5 | Total
Abdul Bah | 17.5 | 38.75 | 31.75 | 37.75 | 27.5 | 153.25
Ethan Hartman | 15 | 27 | 11.75 | 25.5 | 25.75 | 105
Alberto Hernandez | 17.5 | 42.25 | 30.25 | 34 | 30.25 | 154.25
Luke Matthews | 21.5 | 46 | 26.5 | 62.5 | 32 | 188.5
Kenneth Le | 16.25 | 32.25 | 30.25 | 30.5 | 27.25 | 136.5
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
| 0 | 0 | 0 | 0 | 0 | 0
WBS Element | Timesheet 1 | Timesheet 2 | Timesheet 3 | Timesheet 4 | Timesheet 5 | Total
ANALYSIS | 0 | 0 | 0 | 0 | 0 | 0
ASSEMBLY | 0 | 0 | 0 | 0 | 3.5 | 3.5
DESIGN | 0 | 1.5 | 51.75 | 110 | 56.75 | 220
DOCUMENT - ADMIN | 1.25 | 4.5 | 1.5 | 0.5 | 20.5 | 28.25
DOCUMENT - TECH | 0 | 0 | 12.5 | 11.25 | 4.5 | 28.25
FABRICATION | 0 | 0 | 0 | 0 | 0 | 0
MENTOR | 6 | 5.25 | 6.5 | 8.5 | 5.5 | 31.75
OUTREACH | 0 | 0 | 0 | 0 | 0 | 0
PLAN | 16.5 | 4.25 | 6.5 | 24.5 | 20.25 | 72
PROCUREMENT | 0 | 0 | 0 | 0.5 | 6 | 6.5
RESEARCH | 30.5 | 35 | 10 | 21 | 14.75 | 111.25
SOW | 8.75 | 4.75 | 0 | 0 | 0 | 13.5
SUPPORTER | 14.75 | 4 | 9 | 14 | 11 | 52.75
TEST | 0 | 0 | 0 | 0 | 0 | 0

## Timesheet 1
Team Member Name | Total Timesheet Hours | Timesheet 1 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Abdul Bah | 17.5 | QORVO_RADIO2 | ANALYSIS | 0
Ethan Hartman | 15 |  | ASSEMBLY | 0
Alberto Hernandez | 17.5 |  | DESIGN | 0
Luke Matthews | 21.5 |  | DOCUMENT - ADMIN | 1.25
Kenneth Le | 16.25 |  | DOCUMENT - TECH | 0
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 6
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 16.5
| 0 |  | PROCUREMENT | 0
|  |  | RESEARCH | 40.5
|  | Download and Complete in Excel | SOW | 8.75
|  | GRAY boxes are autofilled | SUPPORTER | 14.75
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2025-08-22 | Luke Matthews | Project Understanding |  | 10:00 | 11:00 | 1 | RESEARCH
2025-08-22 | Luke Matthews | Team Meeting for Team contract |  | 9:00 | 10:00 | 1 | PLAN
2025-08-22 | Luke Matthews | First Mentor Meeting |  | 12:15 | 13:15 | 1 | MENTOR
2025-08-26 | Luke Matthews | SOW Development |  | 21:00 | 22:30 | 1.5 | SOW
2025-08-26 | Luke Matthews | Meeting with Andrew Bowman |  | 8:00 | 9:30 | 1.5 | PLAN
2025-08-29 | Luke Matthews | Team Contract Revision Meeting |  | 9:00 | 9:30 | 0.5 | PLAN
2025-08-29 | Luke Matthews | Mentor Meeting |  | 12:15 | 13:15 | 1 | MENTOR
2025-08-22 | Luke Matthews | Minutes of the Meeting template creation |  | 10:30 | 11:00 | 0.5 | DOCUMENT - ADMIN
2025-08-27 | Luke Matthews | Kick off Breakfast |  | 7:15 | 10:00 | 2.75 | SUPPORTER
2025-08-27 | Luke Matthews | Team Contract formating |  | 21:30 | 22:00 | 0.5 | DOCUMENT - ADMIN
2025-09-29 | Luke Matthews | QORVO_RADIO project reserach/understanding |  | 11:00 | 12:15 | 1.25 | RESEARCH
2025-09-29 | Luke Matthews | QORVO_RADIO project reserach/understanding |  | 15:15 | 15:30 | 0.25 | RESEARCH
2025-09-02 | Luke Matthews | QORVO_RADIO project reserach/understanding |  | 16:00 | 16:15 | 0.25 | RESEARCH
2025-08-29 | Luke Matthews | FPGA Research |  | 15:30 | 16:00 | 0.5 | RESEARCH
2025-09-02 | Luke Matthews | Hardware Logic blocks |  | 15:45 | 16:00 | 0.25 | RESEARCH
2025-08-31 | Luke Matthews | Hardware Logic blocks |  | 14:15 | 14:30 | 0.25 | RESEARCH
2025-08-29 | Luke Matthews | Dev Kit research |  | 16:00 | 16:15 | 0.25 | RESEARCH
2025-08-22 | Abdul Bah | Team Meeting |  | 12:15 | 13:15 | 1 | PLAN
2025-08-29 | Abdul Bah | Team Meeting |  | 12:15 | 13:15 | 1 | PLAN
2025-09-01 | Luke Matthews | Dev Kit research |  | 13:15 | 13:30 | 0.25 | RESEARCH
2025-08-31 | Luke Matthews | Dev Kit research |  | 12:00 | 14:15 | 2.25 | RESEARCH
2025-08-26 | Abdul Bah | Meeting with Andrew Bowman |  | 8:00 | 9:30 | 1.5 | PLAN
2025-08-31 | Abdul Bah | Software and PCB Research |  | 15:30 | 18:00 | 2.5 | RESEARCH
2025-09-01 | Abdul Bah | DevKit Research |  | 18:00 | 22:00 | 4 | RESEARCH
2025-09-03 | Luke Matthews | Dev Kit research |  | 10:00 | 12:00 | 2 | RESEARCH
2025-08-27 | Abdul Bah | Kick off Breakfast |  | 7:30 | 10:00 | 2.5 | SUPPORTER
2025-09-04 | Luke Matthews | SOW Revisions |  | 12:45 | 13:15 | 0.5 | SOW
2025-09-04 | Luke Matthews | FPGA and DEV board USB-C Research |  | 13:15 | 13:30 | 0.25 | RESEARCH
2025-09-04 | Luke Matthews | SOW Revisions meeting |  | 20:30 | 21:00 | 0.5 | PLAN
2025-09-04 | Abdul Bah | DevKit Research |  | 15:30 | 19:30 | 4 | RESEARCH
2025-08-30 | Kenneth Le | DevKit SDK Research and Downloading |  | 13:00 | 19:00 | 6 | RESEARCH
2025-09-04 | Kenneth Le | SOW Revisions |  | 20:30 | 21:00 | 0.5 | SOW
2025-09-04 | Kenneth Le | Download SDK Guide |  | 19:45 | 20:30 | 0.75 | RESEARCH
2025-08-27 | Kenneth Le | Kick off Breakfast |  | 7:30 | 10:00 | 2.5 | SUPPORTER
2025-08-26 | Kenneth Le | Meeting with Andrew Bowman |  | 8:00 | 9:30 | 1.5 | PLAN
2025-08-26 | Kenneth Le | Previous Qorvo Team Final Report Research |  | 12:30 | 13:30 | 1 | RESEARCH
2025-09-01 | Alberto Hernandez | Software Research/Downloading |  | 7:00 | 10:00 | 3 | RESEARCH
2025-09-01 | Alberto Hernandez | Learning New Softwares |  | 12:00 | 16:00 | 4 | RESEARCH
2025-09-02 | Alberto Hernandez | Understanding Previous Repo |  | 19:00 | 21:00 | 2 | RESEARCH
2025-09-03 | Alberto Hernandez | Understanding Previous Repo |  | 20:00 | 22:00 | 2 | RESEARCH
2025-08-26 | Alberto Hernandez | Meeting with Andrew Bowman |  | 8:00 | 9:30 | 1.5 | PLAN
2025-09-05 | Alberto Hernandez | Meeting with Industry Partner |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-08-22 | Kenneth Le | First Mentor Meeting |  | 12:30 | 13:15 | 0.75 | MENTOR
2025-08-29 | Kenneth Le | Mentor Meeting |  | 12:15 | 13:15 | 1 | MENTOR
2025-09-04 | Kenneth Le | IoT Wireless Protocols Research |  | 21:30 | 22:00 | 0.5 | RESEARCH
2025-09-05 | Luke Matthews | Industry Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-08-27 | Alberto Hernandez | Kick off Breakfast |  | 7:30 | 10:00 | 2.5 | SUPPORTER
2025-09-05 | Kenneth Le | Industry Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-09-05 | Alberto Hernandez | Team Meeting for SOW |  | 12:00 | 13:15 | 1.25 | SOW
2025-09-04 | Alberto Hernandez | SOW Review |  | 20:30 | 21:15 | 0.75 | SOW
2025-09-05 | Kenneth Le | Team Meeting for SOW & Progress Report |  | 12:00 | 13:15 | 1.25 | SOW
2025-09-05 | Luke Matthews | Weekly Team Meeting |  | 12:15 | 13:15 | 1 | PLAN
2025-09-05 | Abdul Bah | Team Meeting, Porgress Report & SOW |  | 12:15 | 13:15 | 1 | PLAN
2025-08-22 | Ethan Hartman | Team Meeting (Team Contract) |  | 9:00 | 10:00 | 1 | PLAN
2025-08-22 | Ethan Hartman | Mentor Meeting |  | 12:15 | 13:15 | 1 | MENTOR
2025-08-26 | Ethan Hartman | Team Meeting (SOW) |  | 21:00 | 22:30 | 1.5 | SOW
2025-08-26 | Ethan Hartman | Meeting with Andrew Bowman |  | 8:00 | 9:30 | 1.5 | PLAN
2025-08-29 | Ethan Hartman | Team Meeting (Team Contract Revision) |  | 9:00 | 9:30 | 0.5 | PLAN
2025-08-29 | Ethan Hartman | Mentor Meeting |  | 12:15 | 13:15 | 1 | MENTOR
2025-08-27 | Ethan Hartman | Kick off Breakfast |  | 7:30 | 10:00 | 2.5 | SUPPORTER
2025-09-05 | Ethan Hartman | Industry Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-09-04 | Ethan Hartman | Team Meating (SOW Revision) |  | 20:30 | 21:00 | 0.5 | SOW
2025-09-05 | Ethan Hartman | Team Meating (SOW Revision) |  | 12:15 | 13:15 | 1 | SOW
2025-09-05 | Ethan Hartman | Mentor Meeting |  | 13:15 | 13:30 | 0.25 | MENTOR
2025-09-02 | Ethan Hartman | Timesheet Creation |  | 14:30 | 14:45 | 0.25 | DOCUMENT - ADMIN
2025-08-24 | Ethan Hartman | Schedule Planning |  | 15:00 | 15:30 | 0.5 | PLAN
2025-08-31 | Ethan Hartman | Schedule Planning |  | 16:30 | 17:30 | 1 | PLAN
2025-09-03 | Ethan Hartman | Research on enclosure |  | 13:30 | 15:30 | 2 | RESEARCH
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 2
Team Member Name | Total Timesheet Hours | Timesheet 2 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Abdul Bah | 38.75 | QORVO_RADIO2 | ANALYSIS | 0
Ethan Hartman | 27 |  | ASSEMBLY | 0
Alberto Hernandez | 42.25 |  | DESIGN | 1.5
Luke Matthews | 46 |  | DOCUMENT - ADMIN | 4.5
Kenneth Le | 32.25 |  | DOCUMENT - TECH | 0
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 12.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 73.75
| 0 |  | PROCUREMENT | 0
|  |  | RESEARCH | 80.75
|  | Download and Complete in Excel | SOW | 8.75
|  | GRAY boxes are autofilled | SUPPORTER | 14
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2025-09-05 | Kenneth Le | Progress Report |  | 18:45 | 19:15 | 0.5 | PLAN
2025-09-06 | Luke Matthews | Gantt Chart |  | 9:00 | 10:15 | 1.25 | DOCUMENT - ADMIN
2025-09-06 | Luke Matthews | Progress Report |  | 10:15 | 10:30 | 0.25 | PLAN
2025-09-07 | Alberto Hernandez | Progress Report |  | 13:00 | 13:30 | 0.5 | PLAN
2025-09-09 | Alberto Hernandez | Progress Report Review |  | 10:00 | 10:30 | 0.5 | PLAN
2025-09-09 | Luke Matthews | Transeiver Architecture Research |  | 13:00 | 14:15 | 1.25 | RESEARCH
2025-09-09 | Luke Matthews | Transeiver Architecture Research |  | 16:00 | 17:00 | 1 | RESEARCH
2025-09-10 | Luke Matthews | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-10 | Luke Matthews | Qorvo and SL Dev Kit Research |  | 10:15 | 11:30 | 1.25 | RESEARCH
2025-09-10 | Kenneth Le | Mentor Meeting |  | 13:15 | 14:30 | 1.25 | MENTOR
2025-09-10 | Luke Matthews | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-10 | Luke Matthews | SOW revisions |  | 20:30 | 21:15 | 0.75 | SOW
2025-09-11 | Luke Matthews | Dev board research |  | 8:30 | 9:15 | 0.75 | RESEARCH
2025-09-10 | Alberto Hernandez | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-10 | Alberto Hernandez | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-10 | Alberto Hernandez | SOW revisions |  | 20:30 | 21:30 | 1 | SOW
2025-09-10 | Alberto Hernandez | User Interface Research |  | 21:30 | 22:30 | 1 | RESEARCH
2025-09-10 | Alberto Hernandez | Goals Understanding |  | 19:00 | 20:00 | 1 | RESEARCH
2025-09-11 | Alberto Hernandez | Gateway Research |  | 9:30 | 11:00 | 1.5 | RESEARCH
2025-09-11 | Alberto Hernandez | User Interface Research |  | 11:00 | 12:00 | 1 | RESEARCH
2025-09-11 | Alberto Hernandez | Peripheral Understanding |  | 12:00 | 13:30 | 1.5 | RESEARCH
2025-09-11 | Luke Matthews | Remote Device research |  | 15:45 | 17:00 | 1.25 | RESEARCH
2025-09-11 | Kenneth Le | SOW revisions & Progress Report |  | 19:00 | 20:00 | 1 | SOW
2025-09-11 | Kenneth Le | Progress Report Revision |  | 20:00 | 20:30 | 0.5 | PLAN
2025-09-11 | Kenneth Le | Mesh Networking Research |  | 20:30 | 21:30 | 1 | RESEARCH
2025-09-11 | Kenneth Le | QPG6200L Peripheral Applications |  | 21:30 | 22:30 | 1 | RESEARCH
2025-09-12 | Kenneth Le | QPG6200L Peripheral & Overview |  | 10:45 | 12:00 | 1.25 | RESEARCH
2025-09-12 | Kenneth Le | Serial Communications with QPG6200L (UART) |  | 14:30 | 15:30 | 1 | RESEARCH
2025-09-13 | Kenneth Le | UART, USB, I2C/I2S Research |  | 12:45 | 14:45 | 2 | RESEARCH
2025-09-09 | Abdul Bah | Transciever/ Receiver Research |  | 21:00 | 22:30 | 1.5 | RESEARCH
2025-09-10 | Abdul Bah | Progress Report |  | 20:30 | 21:30 | 1 | PLAN
2025-09-10 | Abdul Bah | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-10 | Abdul Bah | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-10 | Abdul Bah | DevKit Research |  | 14:00 | 15:00 | 1 | RESEARCH
2025-09-11 | Abdul Bah | SOW Revisions |  | 20:30 | 21:30 | 1 | SOW
2025-09-11 | Abdul Bah | Remote Device research |  | 18:00 | 19:00 | 1 | RESEARCH
2025-09-12 | Abdul Bah | DevKit Research and Remote Device research |  | 14:00 | 15:30 | 1.5 | RESEARCH
2025-09-13 | Abdul Bah | DEvkit Research and Remote Device research |  | 19:30 | 20:00 | 0.5 | RESEARCH
2025-09-15 | Kenneth Le | Demonstration Brainstorm/Ideas |  | 12:30 | 13:15 | 0.75 | RESEARCH
2025-09-16 | Alberto Hernandez | QPG200L Peripheral understanding |  | 12:00 | 13:30 | 1.5 | RESEARCH
2025-09-11 | Alberto Hernandez | SOW & Progress Report Revisions |  | 19:00 | 20:15 | 1.25 | SOW
2025-09-17 | Alberto Hernandez | Remote Device research |  | 10:30 | 11:45 | 1.25 | RESEARCH
2025-09-17 | Alberto Hernandez | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-17 | Kenneth Le | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-17 | Kenneth Le | One-Page Summary |  | 14:45 | 15:45 | 1 | RESEARCH
2025-09-17 | Luke Matthews | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-17 | Luke Matthews | One-Page Summary |  | 16:30 | 17:00 | 0.5 | RESEARCH
2025-09-17 | Luke Matthews | Minutes of the Meeting Template update |  | 15:45 | 16:30 | 0.75 | DOCUMENT - ADMIN
2025-09-16 | Luke Matthews | Expo demo devices Research |  | 16:00 | 17:00 | 1 | RESEARCH
2025-09-17 | Luke Matthews | Expo demo devices Research |  | 10:00 | 10:45 | 0.75 | RESEARCH
2025-09-17 | Luke Matthews | Perfromance Specs and SOW revisions |  | 17:30 | 18:15 | 0.75 | SOW
2025-09-17 | Luke Matthews | Expo demo devices Research |  | 18:15 | 18:45 | 0.5 | RESEARCH
2025-09-17 | Alberto Hernandez | One Page Summary |  | 18:30 | 19:30 | 1 | RESEARCH
2025-09-17 | Alberto Hernandez | SOW Standards |  | 19:30 | 20:00 | 0.5 | SOW
2025-09-17 | Alberto Hernandez | Protocol Research |  | 14:00 | 15:30 | 1.5 | RESEARCH
2025-09-17 | Luke Matthews | Sponsor meeting slideshow prep |  | 20:30 | 21:00 | 0.5 | PLAN
2025-09-17 | Luke Matthews | Sponsor meeting slideshow prep |  | 22:15 | 23:45 | 1.5 | PLAN
2025-09-18 | Luke Matthews | Sponsor meeting slideshow prep |  | 9:00 | 9:30 | 0.5 | PLAN
2025-09-18 | Luke Matthews | Ultrasonic Sesnor Research |  | 9:30 | 10:00 | 0.5 | RESEARCH
2025-09-18 | Luke Matthews | Minutes of the Meeting Agenda update |  | 13:15 | 13:45 | 0.5 | PLAN
2025-09-18 | Luke Matthews | Ultrasonic Sesnor Research |  | 13:45 | 14:15 | 0.5 | RESEARCH
2025-09-18 | Kenneth Le | Decision Matrices |  | 16:30 | 17:00 | 0.5 | PLAN
2025-09-18 | Kenneth Le | PDMs, PWM, ADC’s Research |  | 20:45 | 22:30 | 1.75 | RESEARCH
2025-09-18 | Kenneth Le | Slideshow Prep |  | 22:30 | 23:45 | 1.25 | PLAN
2025-09-04 | Ethan Hartman | Green Badge Certification |  | 19:00 | 20:00 | 1 | PLAN
2025-09-07 | Ethan Hartman | Progress Report |  | 22:00 | 23:30 | 1.5 | PLAN
2025-09-08 | Ethan Hartman | Meeting Planning |  | 16:00 | 16:30 | 0.5 | PLAN
2025-09-10 | Ethan Hartman | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-10 | Ethan Hartman | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-11 | Ethan Hartman | SOW Revisions |  | 23:00 | 23:30 | 0.5 | SOW
2025-09-12 | Ethan Hartman | SOW Revisions |  | 12:00 | 13:30 | 1.5 | SOW
2025-09-14 | Ethan Hartman | Enclosure Research |  | 15:00 | 17:30 | 2.5 | RESEARCH
2025-09-17 | Ethan Hartman | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-17 | Ethan Hartman | SOW Revision |  | 23:00 | 23:30 | 0.5 | SOW
2025-09-18 | Alberto Hernandez | Slideshow Prep |  | 23:00 | 23:45 | 0.75 | PLAN
2025-09-19 | Alberto Hernandez | Sponser Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-18 | Alberto Hernandez | Electrical Component Research |  | 10:00 | 13:00 | 3 | RESEARCH
2025-09-19 | Kenneth Le | Sponser Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-19 | Kenneth Le | Decision Matrices Plan |  | 12:15 | 13:15 | 1 | PLAN
2025-09-19 | Luke Matthews | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-19 | Luke Matthews | Decision Matrices Plan |  | 12:15 | 13:15 | 1 | PLAN
2025-09-19 | Kenneth Le | Decision Matrix and demo discussion |  | 15:30 | 18:00 | 2.5 | PLAN
2025-09-19 | Luke Matthews | Decision Matrix and demo discussion |  | 15:30 | 18:15 | 2.75 | PLAN
2025-09-19 | Alberto Hernandez | Decision Matrix Plan |  | 12:15 | 13:15 | 1 | PLAN
2025-09-19 | Alberto Hernandez | Decision Matrix and demo discussion |  | 15:30 | 18:15 | 2.75 | PLAN
2025-09-21 | Luke Matthews | Soil Moister sensor research and decision matrix |  | 13:00 | 14:45 | 1.75 | RESEARCH
2025-09-21 | Luke Matthews | Speaker research and decision matrix |  | 14:45 | 15:45 | 1 | RESEARCH
2025-09-21 | Luke Matthews | Ultrasonic Sensor Research and decision matrix |  | 15:45 | 16:00 | 0.25 | RESEARCH
2025-09-21 | Luke Matthews | Entryway Demo Idea research |  | 19:45 | 21:30 | 1.75 | RESEARCH
2025-09-22 | Luke Matthews | Creation and setup of CDR presentation |  | 15:45 | 16:15 | 0.5 | DOCUMENT - ADMIN
2025-09-22 | Luke Matthews | Antenna Research |  | 16:15 | 17:45 | 1.5 | RESEARCH
2025-09-22 | Kenneth Le | Demo Device Research |  | 18:00 | 19:00 | 1 | RESEARCH
2025-09-22 | Luke Matthews | PCB Logic Design |  | 18:15 | 18:45 | 0.5 | RESEARCH
2025-09-22 | Kenneth Le | CDR Plan Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-09-22 | Alberto Hernandez | Mesh Topology Research |  | 13:00 | 15:15 | 2.25 | RESEARCH
2025-09-22 | Alberto Hernandez | CDR Plan Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-09-22 | Kenneth Le | Gateway Research |  | 20:00 | 21:00 | 1 | RESEARCH
2025-09-22 | Luke Matthews | CDR Plan Meeting and prep |  | 18:45 | 20:00 | 1.25 | PLAN
2025-09-22 | Luke Matthews | CDR Slides, and research |  | 22:00 | 23:15 | 1.25 | RESEARCH
2025-09-23 | Alberto Hernandez | CDR Decision Matrix for Gateway/Interface |  | 11:30 | 13:30 | 2 | RESEARCH
2025-09-23 | Luke Matthews | J-Link Research |  | 13:00 | 14:00 | 1 | RESEARCH
2025-09-23 | Luke Matthews | CDR slide prep and research |  | 15:30 | 17:15 | 1.75 | RESEARCH
2025-09-23 | Luke Matthews | CDR slide prep |  | 19:30 | 20:30 | 1 | PLAN
2025-09-23 | Kenneth Le | CDR slide prep |  | 21:45 | 23:45 | 2 | PLAN
2025-09-23 | Luke Matthews | CDR slide prep |  | 21:00 | 22:45 | 1.75 | PLAN
2025-09-23 | Alberto Hernandez | CDR Slide prep |  | 19:00 | 21:00 | 2 | PLAN
2025-09-24 | Alberto Hernandez | CDR Slide prep |  | 7:00 | 8:30 | 1.5 | PLAN
2025-09-24 | Kenneth Le | CDR Mentor Meeting |  | 9:00 | 9:45 | 0.75 | MENTOR
2025-09-24 | Kenneth Le | CDR Revision Meeting |  | 13:30 | 14:15 | 0.75 | PLAN
2025-09-24 | Kenneth Le | Wireless Logic Diagrams |  | 14:30 | 15:45 | 1.25 | RESEARCH
2025-09-24 | Alberto Hernandez | CDR Revision Meeting |  | 13:15 | 14:15 | 1 | PLAN
2025-09-24 | Luke Matthews | CDR Revision Meeting |  | 13:15 | 14:15 | 1 | PLAN
2025-09-24 | Luke Matthews | CDR Slide Revisions |  | 19:30 | 20:45 | 1.25 | PLAN
2025-09-24 | Alberto Hernandez | CDR Slide Revisions |  | 19:30 | 20:45 | 1.25 | PLAN
2025-09-24 | Alberto Hernandez | CDR Slides and User Interface/Display Research |  | 21:00 | 22:30 | 1.5 | RESEARCH
2025-09-25 | Luke Matthews | CDR Slide Revisions |  | 13:00 | 14:15 | 1.25 | PLAN
2025-09-25 | Kenneth Le | CDR Slide Prep |  | 17:00 | 18:00 | 1 | PLAN
2025-09-25 | Kenneth Le | CDR Slide Team Practice |  | 19:15 | 21:00 | 1.75 | PLAN
2025-09-25 | Alberto Hernandez | CDR Slide Team Practice |  | 19:00 | 21:00 | 2 | PLAN
2025-09-25 | Alberto Hernandez | Peer Review |  | 11:00 | 11:15 | 0.25 | DOCUMENT - ADMIN
2025-09-24 | Kenneth Le | Peer Review |  | 17:00 | 17:30 | 0.5 | DOCUMENT - ADMIN
2025-09-26 | Kenneth Le | CDR Presentation with Sponsers |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-09-26 | Alberto Hernandez | CDR Presentation with Sponsors |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-09-25 | Luke Matthews | CDR Slide Team Practice |  | 19:00 | 21:00 | 2 | PLAN
2025-09-26 | Luke Matthews | CDR Presentation with Sponsors |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-09-21 | Luke Matthews | Peer Evaluation |  | 12:00 | 12:30 | 0.5 | DOCUMENT - ADMIN
2025-09-25 | Abdul Bah | Peer Evaluation |  | 23:00 | 23:15 | 0.25 | DOCUMENT - ADMIN
2025-09-16 | Abdul Bah | Slideshow Prep |  | 21:00 | 22:30 | 1.5 | PLAN
2025-09-17 | Abdul Bah | Device Research |  | 18:00 | 21:00 | 3 | RESEARCH
2025-09-18 | Abdul Bah | Demo and Slideshow Prep |  | 18:30 | 21:30 | 3 | PLAN
2025-09-17 | Abdul Bah | Mentor Meeting |  | 13:15 | 14:15 | 1 | MENTOR
2025-09-19 | Abdul Bah | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-17 | Abdul Bah | One Page Summary |  | 19:00 | 20:00 | 1 | RESEARCH
2025-09-19 | Abdul Bah | CDR, Decision Matrix, Demo Meeting |  | 15:30 | 18:15 | 2.75 | PLAN
2025-09-20 | Abdul Bah | CDR and Device Research |  | 17:00 | 19:00 | 2 | RESEARCH
2025-09-21 | Abdul Bah | Device Research |  | 10:00 | 12:00 | 2 | RESEARCH
2025-09-21 | Abdul Bah | Device Research |  | 20:30 | 22:30 | 2 | RESEARCH
2025-09-22 | Abdul Bah | Research |  | 12:00 | 15:00 | 3 | RESEARCH
2025-09-22 | Abdul Bah | CDR Plan Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-09-22 | Abdul Bah | Component Reseach |  | 20:30 | 21:30 | 1 | RESEARCH
2025-09-23 | Abdul Bah | Component Reseach |  | 13:00 | 16:00 | 3 | RESEARCH
2025-09-23 | Abdul Bah | CDR slide prep and research |  | 22:00 | 23:45 | 1.75 | RESEARCH
2025-09-24 | Abdul Bah | Mentor Meeting |  | 9:00 | 9:45 | 0.75 | MENTOR
2025-09-24 | Abdul Bah | CDR Revision Meeting |  | 13:15 | 14:15 | 1 | PLAN
2025-09-24 | Abdul Bah | CDR Slide Prep and Revisions |  | 17:00 | 18:45 | 1.75 | PLAN
2025-09-25 | Abdul Bah | CDR Slide Prep |  | 12:30 | 15:30 | 3 | PLAN
2025-09-25 | Abdul Bah | CDR Slide Presentation Practice |  | 19:00 | 21:00 | 2 | PLAN
2025-09-26 | Abdul Bah | CDR Presentation with Sponsors |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-09-19 | Ethan Hartman | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-09-19 | Ethan Hartman | Decision Matrix and demo discussion |  | 15:30 | 18:15 | 2.75 | PLAN
2025-09-19 | Ethan Hartman | Decision Matrix Plan |  | 12:15 | 13:15 | 1 | PLAN
2025-09-22 | Ethan Hartman | Device organization research |  | 15:30 | 16:30 | 1 | RESEARCH
2025-09-22 | Ethan Hartman | CDR Plan Meeting and prep |  | 19:00 | 20:00 | 1 | PLAN
2025-09-23 | Ethan Hartman | CDR Slide Prep |  | 16:00 | 17:30 | 1.5 | PLAN
2025-09-24 | Ethan Hartman | CDR Mentor Meeting |  | 9:00 | 9:45 | 0.75 | MENTOR
2025-09-24 | Ethan Hartman | CDR Slide Revisions |  | 13:15 | 14:15 | 1 | PLAN
2025-09-24 | Ethan Hartman | CDR Slide Revisions |  | 16:00 | 17:00 | 1 | PLAN
2025-09-25 | Ethan Hartman | Enclosure Concept Design |  | 10:00 | 11:00 | 1 | DESIGN
2025-09-25 | Ethan Hartman | CDR Slide Team Practice |  | 19:00 | 21:00 | 2 | PLAN
2025-09-25 | Ethan Hartman | Peer Reviews |  | 21:30 | 22:00 | 0.5 | DOCUMENT - ADMIN
2025-09-25 | Ethan Hartman | Enclosure Redesign |  | 22:00 | 22:30 | 0.5 | DESIGN
2025-09-26 | Ethan Hartman | CDR Presentation with Sponsors |  | 9:00 | 10:00 | 1 | SUPPORTER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 3
Team Member Name | Total Timesheet Hours | Timesheet 3 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Abdul Bah | 31.75 | QORVO_RADIO2 | ANALYSIS | 0
Ethan Hartman | 11.75 |  | ASSEMBLY | 0
Alberto Hernandez | 30.25 |  | DESIGN | 79
Luke Matthews | 26.5 |  | DOCUMENT - ADMIN | 1.5
Kenneth Le | 30.25 |  | DOCUMENT - TECH | 12.5
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 6.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 6.5
| 0 |  | PROCUREMENT | 0
|  |  | RESEARCH | 15.5
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 9
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2025-09-29 | Luke Matthews | KiCad Research and development |  | 19:00 | 19:45 | 0.75 | DESIGN
2025-09-30 | Luke Matthews | KiCad Schematic Editor |  | 9:30 | 10:00 | 0.5 | DESIGN
2025-09-30 | Luke Matthews | KiCad Schematic Editor |  | 11:15 | 12:00 | 0.75 | DESIGN
2025-09-30 | Luke Matthews | KiCad Schematic Editor |  | 15:45 | 17:15 | 1.5 | DESIGN
2025-10-01 | Alberto Hernandez | Mentor Meeting |  | 9:30 | 9:45 | 0.25 | DESIGN
2025-10-01 | Kenneth Le | Mentor Meeting |  | 9:30 | 10:00 | 0.5 | MENTOR
2025-10-01 | Luke Matthews | Mentor Meeting |  | 9:30 | 9:45 | 0.25 | MENTOR
2025-10-01 | Luke Matthews | KiCad J-Link and Buck Converter design |  | 9:45 | 11:30 | 1.75 | DESIGN
2025-10-02 | Luke Matthews | KiCad Audio Speaker Design |  | 13:00 | 14:15 | 1.25 | DESIGN
2025-10-02 | Alberto Hernandez | Gateway research |  | 21:00 | 22:45 | 1.75 | RESEARCH
2025-10-03 | Alberto Hernandez | Supporter Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-03 | Luke Matthews | Meet with Abdul |  | 21:00 | 21:30 | 0.5 | PLAN
2025-09-29 | Luke Matthews | Meet with Abdul |  | 21:30 | 22:00 | 0.5 | PLAN
2025-10-03 | Luke Matthews | Supporter Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-03 | Luke Matthews | KiCad circuit schematic development |  | 10:30 | 12:30 | 2 | DESIGN
2025-10-06 | Luke Matthews | KiCad circuit schematic development |  | 11:00 | 13:00 | 2 | DESIGN
2025-10-06 | Luke Matthews | KiCad circuit schematic development |  | 19:00 | 19:45 | 0.75 | DESIGN
2025-10-12 | Luke Matthews | KiCad circuit footprint development |  | 21:00 | 22:00 | 1 | DESIGN
2025-10-03 | Kenneth Le | Supporter Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-13 | Kenneth Le | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-10-13 | Luke Matthews | KiCad circuit footprint development |  | 9:30 | 10:30 | 1 | DESIGN
2025-10-13 | Luke Matthews | KiCad circuit footprint development |  | 15:45 | 17:15 | 1.5 | DESIGN
2025-10-13 | Luke Matthews | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-10-14 | Luke Matthews | FInding the Gaps |  | 16:15 | 16:30 | 0.25 | DOCUMENT - TECH
2025-10-14 | Luke Matthews | Progress Report updates |  | 16:30 | 17:00 | 0.5 | DOCUMENT - TECH
2025-10-16 | Kenneth Le | Mentor Meeting |  | 8:20 | 9:20 | 1 | MENTOR
2025-10-16 | Alberto Hernandez | Mentor Meeting |  | 8:30 | 9:30 | 1 | MENTOR
2025-10-16 | Alberto Hernandez | Progress Report updates |  | 18:00 | 20:00 | 2 | DOCUMENT - TECH
2025-10-16 | Alberto Hernandez | Finding the Gaps |  | 17:30 | 18:00 | 0.5 | DOCUMENT - TECH
2025-10-16 | Alberto Hernandez | Making Part List Table |  | 20:00 | 20:15 | 0.25 | DOCUMENT - ADMIN
2025-10-16 | Alberto Hernandez | Adding Refrences to Progress Report |  | 20:30 | 21:30 | 1 | DOCUMENT - TECH
2025-10-16 | Luke Matthews | Mentor Meeting |  | 8:30 | 9:30 | 1 | MENTOR
2025-10-16 | Luke Matthews | Progress Report #2, and Finding the gaps |  | 19:30 | 20:30 | 1 | DOCUMENT - TECH
2025-10-16 | Luke Matthews | KiCad Footprint Development |  | 20:30 | 22:00 | 1.5 | DESIGN
2025-10-16 | Luke Matthews | KiCad Footprint Development |  | 22:30 | 23:15 | 0.75 | DESIGN
2025-10-12 | Alberto Hernandez | Downloaded Thingsboard and Set it up |  | 20:00 | 22:00 | 2 | DESIGN
2025-10-10 | Alberto Hernandez | Set up for QPG6200L DevKit |  | 6:00 | 8:00 | 2 | DESIGN
2025-10-13 | Alberto Hernandez | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-10-17 | Alberto Hernandez | Supporter Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-11 | Alberto Hernandez | qpg6200-iot-sdk undestanding |  | 7:00 | 8:45 | 1.75 | DESIGN
2025-10-14 | Alberto Hernandez | qpg6200-iot-sdk undestanding |  | 8:00 | 10:00 | 2 | DESIGN
2025-10-16 | Alberto Hernandez | qpg6200-iot-sdk Practice |  | 6:30 | 9:00 | 2.5 | DESIGN
2025-10-17 | Alberto Hernandez | Slide Creation for Supporter Meeting |  | 0:00 | 0:45 | 0.75 | DOCUMENT - TECH
2025-10-17 | Kenneth Le | Slide Creation for Supporter Meeting |  | 0:00 | 1:00 | 1 | DOCUMENT - TECH
2025-10-17 | Kenneth Le | Industry Support Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-15 | Kenneth Le | Progress Report |  | 18:00 | 19:00 | 1 | DOCUMENT - TECH
2025-10-16 | Kenneth Le | Progress Report Updates |  | 21:00 | 22:00 | 1 | DOCUMENT - TECH
2025-10-08 | Kenneth Le | Gateway research |  | 20:30 | 22:30 | 2 | RESEARCH
2025-10-08 | Kenneth Le | Wi-Fi reseach |  | 22:00 | 23:30 | 1.5 | RESEARCH
2025-10-15 | Kenneth Le | Finding the Gaps |  | 17:00 | 18:00 | 1 | DOCUMENT - TECH
2025-10-09 | Kenneth Le | BLE Programing Learning |  | 16:00 | 18:00 | 2 | DESIGN
2025-10-13 | Kenneth Le | Zigbee Programing Learning |  | 18:30 | 21:00 | 2.5 | DESIGN
2025-10-04 | Kenneth Le | Wireless Protocol Planning/Research |  | 21:00 | 22:30 | 1.5 | RESEARCH
2025-10-17 | Alberto Hernandez | Created Team Repo |  | 9:00 | 9:45 | 0.75 | DESIGN
2025-10-17 | Alberto Hernandez | Blink LED on Devkit |  | 10:00 | 11:30 | 1.5 | DESIGN
2025-10-12 | Alberto Hernandez | SDK applications/battery monitor |  | 7:00 | 9:00 | 2 | DESIGN
2025-10-09 | Alberto Hernandez | ThingsBoard installation Matrix |  | 20:00 | 21:00 | 1 | DESIGN
2025-10-15 | Alberto Hernandez | SoC RF Communication Understanding |  | 20:00 | 22:30 | 2.5 | DESIGN
2025-10-09 | Alberto Hernandez | Researched setup for SoC |  | 6:00 | 7:45 | 1.75 | RESEARCH
2025-10-10 | Kenneth Le | Thread Programing Learning |  | 20:00 | 21:00 | 1 | DESIGN
2025-10-03 | Kenneth Le | J-Link Research |  | 14:00 | 14:45 | 0.75 | RESEARCH
2025-10-14 | Kenneth Le | SDK applications |  | 19:00 | 21:00 | 2 | DESIGN
2025-10-07 | Kenneth Le | Thread Programing Learning |  | 20:00 | 22:00 | 2 | DESIGN
2025-10-17 | Luke Matthews | Industry Support Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-17 | Luke Matthews | KiCad Footprint development |  | 9:45 | 12:15 | 2.5 | DESIGN
2025-09-30 | Abdul Bah | KiCad Research and development |  | 1:00 | 2:00 | 1 | RESEARCH
2025-09-30 | Abdul Bah | KiCad Research and development |  | 20:00 | 21:30 | 1.5 | RESEARCH
2025-10-01 | Abdul Bah | Mentor Meeting |  | 9:30 | 9:45 | 0.25 | MENTOR
2025-10-01 | Abdul Bah | KiCad Research and development |  | 16:45 | 17:30 | 0.75 | RESEARCH
2025-10-02 | Abdul Bah | KiCad Symbol development |  | 17:00 | 19:00 | 2 | DESIGN
2025-10-02 | Abdul Bah | KiCad Symbol development |  | 21:30 | 23:00 | 1.5 | DESIGN
2025-10-03 | Abdul Bah | KiCad Symbol development |  | 20:00 | 21:00 | 1 | DESIGN
2025-10-04 | Abdul Bah | KiCad Symbol development |  | 17:45 | 18:45 | 1 | DESIGN
2025-10-05 | Abdul Bah | KiCad Symbol development |  | 21:45 | 22:45 | 1 | DESIGN
2025-10-06 | Abdul Bah | KiCad Symbol development |  | 11:00 | 11:30 | 0.5 | DESIGN
2025-10-06 | Abdul Bah | KiCad Symbol development |  | 19:00 | 20:00 | 1 | DESIGN
2025-10-06 | Abdul Bah | KiCad Symbol development |  | 21:15 | 23:00 | 1.75 | DESIGN
2025-10-07 | Abdul Bah | KiCad Symbol development |  | 9:00 | 9:30 | 0.5 | RESEARCH
2025-10-07 | Abdul Bah | KiCad Symbol development |  | 18:00 | 20:30 | 2.5 | DESIGN
2025-10-07 | Abdul Bah | KiCad Symbol development |  | 21:45 | 23:00 | 1.25 | DESIGN
2025-10-08 | Abdul Bah | KiCad Symbol development |  | 16:00 | 17:00 | 1 | DESIGN
2025-10-08 | Abdul Bah | KiCad Symbol development |  | 19:00 | 21:00 | 2 | DESIGN
2025-10-09 | Abdul Bah | KiCad Footprint development |  | 17:00 | 17:30 | 0.5 | RESEARCH
2025-10-14 | Abdul Bah | KiCad Footprint development |  | 20:00 | 21:00 | 1 | RESEARCH
2025-10-15 | Abdul Bah | KiCad Footprint development |  | 14:00 | 15:00 | 1 | DESIGN
2025-10-15 | Abdul Bah | KiCad Footprint development |  | 20:00 | 22:00 | 2 | DESIGN
2025-10-16 | Abdul Bah | Mentor Meeting |  | 8:30 | 9:30 | 1 | MENTOR
2025-10-16 | Abdul Bah | Progress Report |  | 19:30 | 20:00 | 0.5 | DOCUMENT - TECH
2025-10-16 | Abdul Bah | Find the Gap |  | 20:00 | 20:30 | 0.5 | DOCUMENT - TECH
2025-10-13 | Abdul Bah | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-10-16 | Abdul Bah | KiCad Footprint development |  | 20:30 | 22:00 | 1.5 | DESIGN
2025-10-17 | Abdul Bah | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-17 | Abdul Bah | KiCad Footprint development |  | 9:00 | 10:15 | 1.25 | DESIGN
2025-10-05 | Kenneth Le | Downloading DevKit SDK & Practice |  | 17:00 | 19:30 | 2.5 | DESIGN
2025-10-15 | Kenneth Le | BLE Practice |  | 12:00 | 14:00 | 2 | DESIGN
2025-10-17 | Kenneth Le | SDK applications |  | 12:00 | 14:00 | 2 | DESIGN
2025-10-01 | Ethan Hartman | Mentor Meeting |  | 9:30 | 10:00 | 0.5 | MENTOR
2025-10-03 | Ethan Hartman | Supporter Meeting |  | 20:00 | 21:00 | 1 | SUPPORTER
2025-10-13 | Ethan Hartman | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-10-16 | Ethan Hartman | Mentor Meeting |  | 8:30 | 9:30 | 1 | MENTOR
2025-10-17 | Ethan Hartman | Supporter Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-04 | Ethan Hartman | Enclosure Refinement |  | 15:00 | 18:00 | 3 | DESIGN
2025-10-08 | Ethan Hartman | Research into purchasing |  | 14:00 | 15:00 | 1 | RESEARCH
2025-10-12 | Ethan Hartman | Weekly Planning |  | 22:00 | 22:30 | 0.5 | PLAN
2025-10-15 | Ethan Hartman | Mentor Meeting presentation preparation |  | 23:00 | 23:30 | 0.5 | DOCUMENT - ADMIN
2025-10-16 | Ethan Hartman | Supporter Meeting presentation preparation |  | 23:00 | 23:30 | 0.5 | DOCUMENT - ADMIN
2025-10-16 | Ethan Hartman | Expo Requirements |  | 22:00 | 22:15 | 0.25 | DOCUMENT - ADMIN
2025-10-17 | Ethan Hartman | Progress Report |  | 12:30 | 13:30 | 1 | DOCUMENT - TECH
2025-10-17 | Ethan Hartman | Fill in the Gaps |  | 13:30 | 14:00 | 0.5 | DOCUMENT - TECH
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 4
Team Member Name | Total Timesheet Hours | Timesheet 4 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Abdul Bah | 37.75 | QORVO_RADIO2 | ANALYSIS | 0
Ethan Hartman | 25.5 |  | ASSEMBLY | 0
Alberto Hernandez | 34 |  | DESIGN | 110
Luke Matthews | 62.5 |  | DOCUMENT - ADMIN | 0.5
Kenneth Le | 30.5 |  | DOCUMENT - TECH | 11.25
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 8.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 24.5
| 0 |  | PROCUREMENT | 0.5
|  |  | RESEARCH | 21
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 14
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2025-10-17 | Luke Matthews | KiCad Symbol updates |  | 20:00 | 21:30 | 1.5 | DESIGN
2025-10-19 | Luke Matthews | KiCad Symbol and footprint updates |  | 11:30 | 16:00 | 4.5 | DESIGN
2025-10-19 | Luke Matthews | External component package |  | 18:00 | 18:45 | 0.75 | DOCUMENT - TECH
2025-10-19 | Luke Matthews | LED Light strip connections |  | 18:45 | 20:15 | 1.5 | DESIGN
2025-10-20 | Luke Matthews | Parts list update |  | 15:45 | 17:00 | 1.25 | DOCUMENT - TECH
2025-10-20 | Luke Matthews | KiCad footprint imports |  | 17:00 | 17:15 | 0.25 | DESIGN
2025-10-20 | Luke Matthews | KiCad Footprint imports and USB A design |  | 21:00 | 22:30 | 1.5 | DESIGN
2025-10-20 | Luke Matthews | KiCad Footprint revisions |  | 22:45 | 23:15 | 0.5 | DESIGN
2025-10-21 | Luke Matthews | KiCad Footprint revisions |  | 15:45 | 17:00 | 1.25 | DESIGN
2025-10-21 | Luke Matthews | KiCad Footprint revisions |  | 20:30 | 22:00 | 1.5 | DESIGN
2025-10-21 | Alberto Hernandez | SDK Troubleshooting |  | 18:30 | 23:30 | 5 | DESIGN
2025-10-22 | Alberto Hernandez | SDK Troubleshooting |  | 0:00 | 1:00 | 1 | DESIGN
2025-10-22 | Luke Matthews | Sponsor Meeting |  | 7:45 | 8:45 | 1 | SUPPORTER
2025-10-22 | Luke Matthews | Ki Cad Electrical rules checker |  | 9:30 | 11:45 | 2.25 | DESIGN
2025-10-23 | Luke Matthews | Ki Cad Electrical rules checker |  | 8:00 | 9:45 | 1.75 | DESIGN
2025-10-23 | Luke Matthews | Ki Cad Electrical rules checker |  | 15:30 | 16:15 | 0.75 | DESIGN
2025-10-23 | Luke Matthews | Ki Cad Electrical rules checker and intial PCB layout |  | 21:00 | 22:15 | 1.25 | DESIGN
2025-10-27 | Luke Matthews | PCB Mounting meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-10-28 | Luke Matthews | PCB Layout Design |  | 13:15 | 14:15 | 1 | DESIGN
2025-10-28 | Luke Matthews | PCB Layout Design |  | 15:30 | 17:15 | 1.75 | DESIGN
2025-10-29 | Luke Matthews | PCB Layout Design |  | 10:30 | 11:30 | 1 | DESIGN
2025-10-29 | Luke Matthews | Meet with Abdul |  | 16:00 | 16:15 | 0.25 | PLAN
2025-10-29 | Luke Matthews | Update USB-A Footprint |  | 16:15 | 16:30 | 0.25 | DESIGN
2025-10-29 | Luke Matthews | KiCad Designer Rules Checker |  | 18:00 | 18:30 | 0.5 | DESIGN
2025-10-27 | Alberto Hernandez | SDK Troubleshooting |  | 18:00 | 21:30 | 3.5 | DESIGN
2025-10-28 | Alberto Hernandez | QPG6200 DK Flashing |  | 19:00 | 22:00 | 3 | DESIGN
2025-10-29 | Alberto Hernandez | Learning to use Jlink and PuTTY |  | 19:00 | 23:00 | 4 | DESIGN
2025-10-29 | Alberto Hernandez | Slide Creation |  | 23:00 | 23:45 | 0.75 | DOCUMENT - TECH
2025-10-30 | Alberto Hernandez | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-10-30 | Luke Matthews | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-10-31 | Luke Matthews | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-10-31 | Luke Matthews | LDO development |  | 10:30 | 13:15 | 2.75 | DESIGN
2025-10-31 | Luke Matthews | General PCB Trace layout Design |  | 15:00 | 16:15 | 1.25 | DESIGN
2025-11-02 | Luke Matthews | KiCad PCB development |  | 11:30 | 14:30 | 3 | DESIGN
2025-11-03 | Luke Matthews | KiCad PCB development |  | 8:45 | 10:15 | 1.5 | DESIGN
2025-11-03 | Luke Matthews | KiCad PCB development |  | 13:00 | 14:15 | 1.25 | DESIGN
2025-11-03 | Luke Matthews | KiCad PCB development |  | 16:00 | 17:15 | 1.25 | DESIGN
2025-11-03 | Luke Matthews | Antenna 50 Ohm connection design research |  | 21:00 | 22:15 | 1.25 | DESIGN
2025-11-03 | Luke Matthews | Team Meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-11-04 | Luke Matthews | Qorvo and UNCC Logo implementation |  | 9:00 | 10:00 | 1 | DESIGN
2025-11-04 | Luke Matthews | Qorvo and UNCC Logo implementation |  | 11:00 | 12:00 | 1 | DESIGN
2025-11-04 | Luke Matthews | Qorvo and UNCC Logo implementation |  | 13:00 | 14:00 | 1 | DESIGN
2025-11-04 | Luke Matthews | Trace Width calculations |  | 16:15 | 17:00 | 0.75 | DESIGN
2025-11-04 | Luke Matthews | PDR Slide Prep |  | 15:30 | 16:15 | 0.75 | DESIGN
2025-10-31 | Alberto Hernandez | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-03 | Alberto Hernandez | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-05 | Alberto Hernandez | Mentor Meeting |  | 9:00 | 10:00 | 1 | MENTOR
2025-11-05 | Luke Matthews | Mentor meeting |  | 9:00 | 10:00 | 1 | MENTOR
2025-11-05 | Luke Matthews | Power Calculations |  | 10:15 | 11:30 | 1.25 | DESIGN
2025-11-05 | Luke Matthews | antenna width calc |  | 16:00 | 16:30 | 0.5 | DESIGN
2025-11-05 | Luke Matthews | Meeting with Russ |  | 16:30 | 17:30 | 1 | SUPPORTER
2025-11-05 | Luke Matthews | Team Meeting |  | 19:00 | 20:30 | 1.5 | PLAN
2025-11-05 | Luke Matthews | LDO and DAC updates |  | 20:30 | 23:30 | 3 | DESIGN
2025-11-06 | Luke Matthews | Antenna connection and filter design |  | 0:00 | 2:15 | 2.25 | DESIGN
2025-11-06 | Luke Matthews | Power Calculations |  | 2:15 | 2:45 | 0.5 | DESIGN
2025-11-06 | Luke Matthews | BOM updates |  | 2:45 | 3:00 | 0.25 | DOCUMENT - TECH
2025-11-05 | Alberto Hernandez | Team Meeting |  | 19:00 | 20:45 | 1.75 | PLAN
2025-11-05 | Alberto Hernandez | Finding New Tablet |  | 21:30 | 22:00 | 0.5 | RESEARCH
2025-11-06 | Luke Matthews | PDR slide creation |  | 13:00 | 14:00 | 1 | DOCUMENT - TECH
2025-11-06 | Luke Matthews | PDR slide creation |  | 15:45 | 17:00 | 1.25 | DOCUMENT - TECH
2025-11-06 | Alberto Hernandez | Team Meeting |  | 19:15 | 21:15 | 2 | PLAN
2025-11-06 | Alberto Hernandez | Slide Creation |  | 17:30 | 18:30 | 1 | DOCUMENT - TECH
2025-11-06 | Alberto Hernandez | USB Peripheral research |  | 14:30 | 16:00 | 1.5 | RESEARCH
2025-11-06 | Alberto Hernandez | Alternative LED Plan |  | 16:00 | 17:30 | 1.5 | RESEARCH
2025-11-04 | Alberto Hernandez | Peripheral Comm Lines for each Device |  | 19:00 | 21:00 | 2 | DESIGN
2025-11-03 | Alberto Hernandez | SW Development |  | 21:00 | 23:00 | 2 | DESIGN
2025-11-07 | Alberto Hernandez | PDR Supporter Presentation |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-10-20 | Kenneth Le | IoT Flowchart Research |  | 11:00 | 13:00 | 2 | RESEARCH
2025-10-21 | Kenneth Le | IoT Flowchart Research |  | 12:00 | 13:00 | 1 | RESEARCH
2025-10-22 | Kenneth Le | Sponsor Meeting |  | 7:45 | 8:45 | 1 | SUPPORTER
2025-10-23 | Kenneth Le | SDK Practice |  | 13:00 | 17:00 | 4 | DESIGN
2025-10-24 | Kenneth Le | SDK Research |  | 17:00 | 19:30 | 2.5 | DESIGN
2025-10-28 | Kenneth Le | JLink and PuTTy Learning |  | 20:00 | 22:30 | 2.5 | RESEARCH
2025-10-29 | Kenneth Le | JLink and PuTTy Learning |  | 17:00 | 19:30 | 2.5 | RESEARCH
2025-10-30 | Kenneth Le | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-10-31 | Kenneth Le | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-03 | Kenneth Le | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-04 | Kenneth Le | PDR Slide Prep |  | 15:30 | 16:15 | 0.75 | DESIGN
2025-11-05 | Kenneth Le | IoT Flowchart |  | 0:00 | 2:00 | 2 | DESIGN
2025-11-05 | Kenneth Le | Updating Project Plan |  | 2:00 | 3:00 | 1 | PLAN
2025-11-05 | Kenneth Le | Mentor Slide Prep |  | 3:00 | 4:00 | 1 | DESIGN
2025-11-05 | Kenneth Le | Mentor meeting |  | 9:00 | 10:00 | 1 | MENTOR
2025-11-05 | Kenneth Le | Team Meeting |  | 19:00 | 20:45 | 1.75 | PLAN
2025-11-06 | Kenneth Le | Finalizing Project Plan |  | 13:00 | 13:30 | 0.5 | PLAN
2025-11-06 | Kenneth Le | Updating Flowchart |  | 18:00 | 19:00 | 1 | PLAN
2025-11-06 | Kenneth Le | Team Meeting/Practice for PDR |  | 19:00 | 21:00 | 2 | PLAN
2025-11-07 | Kenneth Le | PDR Supporter Presentation |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-11-07 | Kenneth Le | SSH/SCP Research |  | 11:00 | 11:30 | 0.5 | RESEARCH
2025-11-07 | Luke Matthews | PDR |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-11-07 | Luke Matthews | KiCad revisions |  | 11:00 | 13:00 | 2 | DESIGN
2025-10-21 | Ethan Hartman | Slide Creation |  | 23:00 | 23:30 | 0.5 | DOCUMENT - TECH
2025-10-22 | Ethan Hartman | Sponsor Meeting |  | 7:45 | 8:45 | 1 | SUPPORTER
2025-10-29 | Ethan Hartman | PCB Mounting meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-10-30 | Ethan Hartman | CAD Modeling |  | 15:00 | 18:00 | 3 | DESIGN
2025-10-30 | Ethan Hartman | Mentor meeting |  | 8:30 | 9:30 | 1 | MENTOR
2025-10-31 | Ethan Hartman | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-01 | Ethan Hartman | CAD Modeling |  | 12:00 | 17:00 | 5 | DESIGN
2025-11-03 | Ethan Hartman | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-04 | Ethan Hartman | CAD Modeling |  | 15:00 | 17:00 | 2 | DESIGN
2025-10-30 | Ethan Hartman | Purchase Requisition |  | 10:00 | 10:30 | 0.5 | PROCUREMENT
2025-11-04 | Ethan Hartman | Slide Creation |  | 23:00 | 23:30 | 0.5 | DOCUMENT - ADMIN
2025-11-05 | Ethan Hartman | Mentor meeting |  | 9:00 | 10:00 | 1 | MENTOR
2025-11-05 | Ethan Hartman | PDR Presentation Work |  | 15:00 | 17:00 | 2 | DOCUMENT - TECH
2025-11-05 | Ethan Hartman | Team Meeting |  | 19:00 | 20:45 | 1.75 | PLAN
2025-11-06 | Ethan Hartman | PDR Presentation Work |  | 14:00 | 15:30 | 1.5 | DOCUMENT - TECH
2025-11-06 | Ethan Hartman | Team Meeting |  | 19:00 | 21:00 | 2 | PLAN
2025-11-07 | Ethan Hartman | PDR |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-10-20 | Abdul Bah | PCB Design |  | 19:00 | 21:30 | 2.5 | DESIGN
2025-10-22 | Abdul Bah | PCB |  | 20:00 | 22:00 | 2 | DESIGN
2025-10-23 | Abdul Bah | PCB Antenna |  | 19:00 | 21:00 | 2 | DESIGN
2025-10-24 | Abdul Bah | PCB |  | 16:00 | 17:30 | 1.5 | RESEARCH
2025-10-25 | Abdul Bah | PCB Research |  | 16:30 | 17:00 | 0.5 | RESEARCH
2025-10-26 | Abdul Bah | PCB |  | 15:00 | 18:00 | 3 | DESIGN
2025-10-27 | Abdul Bah | PCB |  | 21:45 | 23:45 | 2 | RESEARCH
2025-10-28 | Abdul Bah | PCB Research and Design |  | 15:00 | 17:30 | 2.5 | DESIGN
2025-10-29 | Abdul Bah | PCB LDO Research and Design |  | 19:00 | 22:00 | 3 | DESIGN
2025-10-31 | Abdul Bah | PCB |  | 16:00 | 18:00 | 2 | RESEARCH
2025-11-02 | Abdul Bah | PCB |  | 16:00 | 17:00 | 1 | RESEARCH
2025-11-03 | Abdul Bah | PCB Research and Design |  | 15:00 | 17:00 | 2 | RESEARCH
2025-11-03 | Abdul Bah | PCB Research and Design |  | 8:00 | 10:00 | 2 | DESIGN
2025-11-05 | Abdul Bah | Mentor Meeting |  | 9:00 | 10:00 | 1 | MENTOR
2025-11-05 | Abdul Bah | Team Meeting |  | 19:00 | 20:45 | 1.75 | PLAN
2025-11-05 | Abdul Bah | PCB |  | 8:45 | 11:45 | 3 | DESIGN
2025-10-22 | Abdul Bah | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-06 | Abdul Bah | Team meeting |  | 19:00 | 21:00 | 2 | PLAN
2025-11-06 | Abdul Bah | PDR Slides |  | 22:00 | 23:00 | 1 | DOCUMENT - TECH
2025-11-07 | Abdul Bah | PDR |  | 9:00 | 10:00 | 1 | SUPPORTER
2025-10-30 | Abdul Bah | Mentor Meeting |  | 8:30 | 9:30 | 1 | MENTOR
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Timesheet 5
Team Member Name | Total Timesheet Hours | Timesheet 5 for | WBS Element (definitions of WBS Elements is on Instructions tab) | Total Timesheet Hours
Abdul Bah | 27.5 | QORVO_RADIO2 | ANALYSIS | 0
Ethan Hartman | 25.75 |  | ASSEMBLY | 3.5
Alberto Hernandez | 30.25 |  | DESIGN | 56.75
Luke Matthews | 32 |  | DOCUMENT - ADMIN | 20.5
Kenneth Le | 27.25 |  | DOCUMENT - TECH | 4.5
| 0 |  | FABRICATION | 0
| 0 |  | MENTOR | 5.5
| 0 |  | OUTREACH | 0
| 0 |  | PLAN | 20.25
| 0 |  | PROCUREMENT | 6
|  |  | RESEARCH | 14.75
|  | Download and Complete in Excel | SOW | 0
|  | GRAY boxes are autofilled | SUPPORTER | 11
|  | remove example team and timesheet entry | TEST | 0
Round to the nearest 15 minutes
Date Work Accomplished | Team Member Name | Description of Work Completed | Task Unique ID From Project Plan | Start Time | End Time | Hours Worked (autofilled) | WBS Element
2025-11-10 | Luke Matthews | KiCad Test header and general revisons |  | 14:00 | 16:30 | 2.5 | DESIGN
2025-11-11 | Luke Matthews | Meeting with Zaheen (11/12) |  | 14:30 | 15:30 | 1 | PLAN
2025-11-10 | Alberto Hernandez | Docker Debugging |  | 8:00 | 10:00 | 2 | DESIGN
2025-11-12 | Alberto Hernandez | Movement Detector firmware |  | 12:00 | 15:30 | 3.5 | DESIGN
2025-11-12 | Alberto Hernandez | Application Creation |  | 20:00 | 23:00 | 3 | DESIGN
2025-11-12 | Alberto Hernandez | Putty Error Fixing |  | 16:00 | 17:30 | 1.5 | DESIGN
2025-11-12 | Alberto Hernandez | Mentor Meeting |  | 18:00 | 19:15 | 1.25 | MENTOR
2025-11-12 | Luke Matthews | Expo Poster and Mentor Meeting presentation creation |  | 21:00 | 22:00 | 1 | DOCUMENT - ADMIN
2025-11-12 | Luke Matthews | Co-planer wave guide research |  | 22:00 | 22:45 | 0.75 | RESEARCH
2025-11-13 | Luke Matthews | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-13 | Luke Matthews | KiCad revisions |  | 12:00 | 14:00 | 2 | DESIGN
2025-11-13 | Luke Matthews | KiCad revisions |  | 15:00 | 17:00 | 2 | DESIGN
2025-11-13 | Luke Matthews | Team Meeting |  | 19:15 | 20:45 | 1.5 | PLAN
2025-11-15 | Luke Matthews | Lighting Research |  | 21:30 | 22:30 | 1 | RESEARCH
2025-11-14 | Luke Matthews | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-11-16 | Luke Matthews | External antenna design and gnd connection |  | 11:00 | 14:45 | 3.75 | DESIGN
2025-11-13 | Alberto Hernandez | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-13 | Alberto Hernandez | Team Meeting |  | 19:15 | 20:45 | 1.5 | PLAN
2025-11-13 | Alberto Hernandez | Poster Work |  | 22:00 | 23:00 | 1 | PLAN
2025-11-13 | Alberto Hernandez | Error Debugging |  | 23:00 | 23:45 | 0.75 | DESIGN
2025-11-14 | Alberto Hernandez | Error Debugging |  | 0:00 | 2:00 | 2 | DESIGN
2025-11-14 | Alberto Hernandez | Audio Tx/Rx Research |  | 2:00 | 4:00 | 2 | RESEARCH
2025-11-17 | Alberto Hernandez | Team Meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-11-17 | Alberto Hernandez | Pie Chart Creating |  | 21:30 | 22:00 | 0.5 | DOCUMENT - ADMIN
2025-11-17 | Luke Matthews | Sponsor Meeting |  | 13:00 | 14:00 | 1 | SUPPORTER
2025-12-05 | Luke Matthews | Antenna Design |  | 17:30 | 18:45 | 1.25 | DESIGN
2025-12-06 | Luke Matthews | Team Meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-12-07 | Luke Matthews | Antenna Design |  | 21:45 | 22:45 | 1 | DESIGN
2025-11-10 | Abdul Bah | Antenna Research |  | 13:00 | 14:30 | 1.5 | RESEARCH
2025-11-11 | Abdul Bah | Antenna Design |  | 11:45 | 12:30 | 0.75 | DESIGN
2025-11-10 | Abdul Bah | Coplanar Waveguide Research |  | 21:30 | 23:00 | 1.5 | RESEARCH
2025-11-11 | Abdul Bah | Copper Pour/Fill Research |  | 17:00 | 18:00 | 1 | RESEARCH
2025-11-11 | Abdul Bah | PCB Design |  | 20:45 | 23:30 | 2.75 | DESIGN
2025-11-08 | Abdul Bah | Research |  | 20:00 | 21:00 | 1 | RESEARCH
2025-11-12 | Abdul Bah | PCB Design |  | 16:30 | 17:00 | 0.5 | DESIGN
2025-11-12 | Abdul Bah | PCB Design |  | 21:00 | 22:00 | 1 | DESIGN
2025-11-14 | Abdul Bah | Research |  | 20:00 | 22:00 | 2 | RESEARCH
2025-11-15 | Abdul Bah | Lighting/LED Research |  | 15:00 | 16:00 | 1 | RESEARCH
2025-11-16 | Abdul Bah | Research |  | 20:30 | 22:00 | 1.5 | RESEARCH
2025-11-17 | Abdul Bah | Design |  | 12:45 | 13:00 | 0.25 | DESIGN
2025-11-17 | Abdul Bah | Sponsor meeting |  | 13:00 | 14:00 | 1 | SUPPORTER
2025-11-17 | Abdul Bah | PCB Design |  | 16:00 | 17:00 | 1 | DESIGN
2025-11-17 | Abdul Bah | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-20 | Abdul Bah | Team Meeting |  | 19:00 | 19:30 | 0.5 | PLAN
2025-11-24 | Abdul Bah | KiCad PCB Schematic Review |  | 17:00 | 19:00 | 2 | DESIGN
2025-11-18 | Abdul Bah | Research |  | 21:30 | 22:00 | 0.5 | RESEARCH
2025-11-21 | Abdul Bah | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-20 | Abdul Bah | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-13 | Abdul Bah | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-21 | Luke Matthews | Sponsor Meeting |  | 8:00 | 9:00 | 1 | SUPPORTER
2025-11-21 | Luke Matthews | KiCad Development |  | 10:00 | 13:30 | 3.5 | DESIGN
2025-11-23 | Luke Matthews | KiCad Development |  | 16:00 | 17:00 | 1 | DESIGN
2025-11-24 | Luke Matthews | JLC PCB Quote Prep |  | 20:00 | 23:00 | 3 | PROCUREMENT
2025-11-29 | Luke Matthews | Final Report |  | 21:30 | 23:00 | 1.5 | DOCUMENT - TECH
2025-11-29 | Alberto Hernandez | Final Report |  | 21:30 | 23:15 | 1.75 | DOCUMENT - ADMIN
2025-11-30 | Alberto Hernandez | Final Report |  | 18:00 | 20:30 | 2.5 | DOCUMENT - ADMIN
2025-11-26 | Alberto Hernandez | Analog Peripheral |  | 8:00 | 10:00 | 2 | DESIGN
2025-11-10 | Kenneth Le | Gateway Developing |  | 19:00 | 21:00 | 2 | DESIGN
2025-11-11 | Kenneth Le | IoT Block Diagram |  | 20:00 | 21:00 | 1 | DOCUMENT - ADMIN
2025-11-12 | Kenneth Le | Mentor Meeting |  | 18:00 | 19:15 | 1.25 | MENTOR
2025-11-13 | Kenneth Le | Gateway Developing with Static IP Addressing |  | 0:00 | 3:00 | 3 | DESIGN
2025-11-13 | Kenneth Le | Slide Creation for Mentor Meeting |  | 3:00 | 5:00 | 2 | DOCUMENT - ADMIN
2025-11-13 | Kenneth Le | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-13 | Kenneth Le | Team Meeting |  | 19:15 | 20:45 | 1.5 | PLAN
2025-11-14 | Kenneth Le | Sponsor Meeting |  | 8:00 | 8:30 | 0.5 | SUPPORTER
2025-11-17 | Kenneth Le | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-19 | Kenneth Le | Gateway Research Purchasing for DCHP |  | 21:00 | 22:00 | 1 | RESEARCH
2025-11-20 | Kenneth Le | Gateway Purchasing for DCHP |  | 18:00 | 19:00 | 1 | PLAN
2025-11-21 | Kenneth Le | Gateway Debugging |  | 11:00 | 12:00 | 1 | DESIGN
2025-11-21 | Kenneth Le | Gateway Debugging |  | 19:00 | 20:30 | 1.5 | DESIGN
2025-11-24 | Kenneth Le | Gateway Debugging |  | 21:00 | 22:00 | 1 | DESIGN
2025-11-25 | Kenneth Le | Gateway Debugging |  | 21:00 | 23:00 | 2 | DESIGN
2025-11-29 | Kenneth Le | Final Report |  | 20:00 | 22:00 | 2 | DOCUMENT - ADMIN
2025-11-30 | Kenneth Le | Final Report |  | 1:00 | 2:00 | 1 | DOCUMENT - ADMIN
2025-11-30 | Kenneth Le | Final Report |  | 19:00 | 20:00 | 1 | DOCUMENT - ADMIN
2025-12-01 | Kenneth Le | Team Meeting |  | 19:00 | 20:30 | 1.5 | PLAN
2025-12-03 | Kenneth Le | Gateway Programming |  | 16:00 | 17:30 | 1.5 | DESIGN
2025-12-01 | Alberto Hernandez | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-12-03 | Alberto Hernandez | Peer Evaluation |  | 12:00 | 12:30 | 0.5 | DOCUMENT - ADMIN
2025-12-03 | Alberto Hernandez | Soldering ultrasonic sensor |  | 18:00 | 18:30 | 0.5 | ASSEMBLY
2025-12-03 | Alberto Hernandez | Configuring DevKit with new sensor |  | 19:00 | 20:45 | 1.75 | DESIGN
2025-12-04 | Luke Matthews | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-12-04 | Luke Matthews | Peer Evaluation |  | 13:00 | 13:15 | 0.25 | DOCUMENT - ADMIN
2025-12-04 | Luke Matthews | Feedback Survey |  | 13:15 | 13:30 | 0.25 | DOCUMENT - ADMIN
2025-12-01 | Abdul Bah | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-30 | Abdul Bah | Final Report |  | 15:00 | 17:00 | 2 | DOCUMENT - TECH
2025-11-30 | Abdul Bah | Final Report |  | 18:00 | 19:00 | 1 | DOCUMENT - TECH
2025-12-04 | Abdul Bah | Feedback Survey |  | 17:30 | 17:45 | 0.25 | DOCUMENT - ADMIN
2025-12-04 | Abdul Bah | Peer Evaluation |  | 17:45 | 18:15 | 0.5 | DOCUMENT - ADMIN
2025-11-13 | Ethan Hartman | Mentor Meeting |  | 8:30 | 9:00 | 0.5 | MENTOR
2025-11-13 | Ethan Hartman | Team Meeting |  | 19:00 | 20:45 | 1.75 | PLAN
2025-11-17 | Ethan Hartman | Team Meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-11-20 | Ethan Hartman | Team Meeting |  | 19:00 | 19:45 | 0.75 | PLAN
2025-11-29 | Ethan Hartman | Final Report |  | 15:00 | 18:00 | 3 | DOCUMENT - ADMIN
2025-11-30 | Ethan Hartman | Final Report |  | 19:00 | 22:00 | 3 | DOCUMENT - ADMIN
2025-12-01 | Ethan Hartman | Team Meeting |  | 19:00 | 20:00 | 1 | PLAN
2025-11-17 | Ethan Hartman | Purchase Requisitions |  | 15:00 | 16:30 | 1.5 | PROCUREMENT
2025-11-28 | Ethan Hartman | Enclosure Design Modification |  | 14:00 | 17:00 | 3 | DESIGN
2025-12-01 | Ethan Hartman | Enclosure Assembly |  | 14:00 | 17:00 | 3 | ASSEMBLY
2025-12-03 | Ethan Hartman | Purchase Requisitions |  | 15:00 | 16:30 | 1.5 | PROCUREMENT
2025-12-05 | Ethan Hartman | Senior Design Expo |  | 9:00 | 15:00 | 6 | SUPPORTER
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## Control Table
Team Members | Work Breakdown Structure Elements
Abdul Bah |  | Set Date range in Data Validation
Ethan Hartman | ANALYSIS | 08/18/2025 - 05/12/2026
Alberto Hernandez | ASSEMBLY
Luke Matthews | DESIGN
Kenneth Le | DOCUMENT - ADMIN
DOCUMENT - TECH
FABRICATION
MENTOR
OUTREACH
PLAN
PROCUREMENT
RESEARCH
SOW
SUPPORTER
TEST

## Instructions
Instructions for completing the Timesheet
Timesheet is designed to work in Excel, download it in Excel, submit it in Excel. Some features and calculations do not work in Google Sheets.
Set up
on Timesheet Dashboard:
List team members Banner names in alphabetical order by last name starting in block A4
Put team name in block L2
Do not modify any other blocks on Timesheet Dashboard worksheet
For the first module, go to Timesheet 1:
Lines 1-21 are autofilled, do not modify.
Beginning on line 22, use dropdown menues to detail work done on the project by each student, each day. Use the drop down menues where available. Catagorize each task as a Work Breakdown Structure element from the drop down menu.
Overwrite the example on line 22 line with your data.
Continue for every team members tasks during that Timesheet period.
Class lectures and quizzes are not logged as project time.
Each subsequent timesheet should use the same base document and move to the next tab.
To submit:
Download the Timesheet as an Excel (.xlsx) document, label the document with your Team name and assignment (Example: CLOISTER_FILLER_Timesheet1) and submit to Canvas.
Do not modify another student's submitted time. If you have concerns about falsification of the timesheet, contact your mentor or instructor of record.
WBS Element | DESCRIPTION
SUPPORTER | Meeting with project supporter, including Kick-Off Breakfast and plant visits for general orientation. Visits to facility with specific research or design purposes should not be included.
MENTOR | Meetings with project mentor or grading instructor. If meeting is with both mentor and supporter, use 'Supporter' code.
SOW | Time spend preparing and modifying the statement of work and requirements. This includes both initial prepration and subsequent modifications.
PLAN | Project planning includes both the preparation of the original plan and its maintenance. Also include meeting time spend organizing and planning tasks. Results of these meetings should be reflected in a Project Plan update.
RESEARCH | Technical investigation of a general nature necessary to understtand the project including library searches and reading, but does not include actual analysis carried out in support of a design. Finding fron time spent researching should be documented in the Google drive.
ANALYSIS | Analytical support of the design includes time spent in activities such as calculations, FEA analysis, circuit simulations, etc.
DESIGN | Design applies to both the creation of candidate designs during the conceptual phase and subsequent development of the selected alternative. Time spent creating ciruit diagrams, models and drawings can appear here or as part of technical documentation depending on the nature of the work.
DOCUMENT - ADMIN | Administrative documentation, such as timesheet preparation, design review preparation, and document preparation.
DOCUMENT - TECHNICAL | Design documentation can include drawings, circuit diagrams and documentation of analytical work carried out in support of the project when it is not a technically creative process. Some judgement should be applied in choosing documentation or design as a WBS category. This distinction should be consistent with the WBS and task description in the project plan.
PROCUREMENT | Preparation of procurement documents, negotiating with suppliers, ordering and picking up parts used in the project. Discussions with suppliers preliminary to design decisions are either research or design activites.
FABRICATION | Machining parts or circuits for the project.
ASSEMBLY | Assembly of the project
TEST | Testing the project and analyzing the test results.
OUTREACH | Time spent using the Senior Design program to promote STEM education or awareness in others.