## Gantt Chart
QORVO_RADIO2 | [6 empty] | Revision Date:4/1/2026
| PROJECT Lead | Ethan Hartman |  |  |  |  | Mentor's Name | [6 empty] | Fareena Saqib and Nan BouSaba
| PROJECT Team members | Luke Matthews, Abdul Bah, Alberto Hernandez, Kenneth Le
Completed
Future
Task ID | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | Module 1 August 18-September 5th | [14 empty] | Module 2 September 6-September 27 | [14 empty] | Module 3 September 28-October 17 | [14 empty] | Module 4 October 19-November 7 | [14 empty] | Module 5 November 8-December 4 | [19 empty] | SD2 Module 1 January 12-January 30 | [14 empty] | SD2 Module 2 February 2-February 20 | [14 empty] | SD2 Module 3 February 23-March 13 | [14 empty] | SD2 Module 4 March 16-April 3 | [14 empty] | SD2 Module 5 April 6-April 24
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12 |  |  |  |  | WEEK 13 |  |  |  |  | WEEK 14 |  |  |  |  | WEEK 15 |  |  |  |  | WEEK 16
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Initiation
1.1 | Team Introductions | Whole Team | 2025-08-18 | 2025-08-22 | 4 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 10 M to WEEK 10 W
1.1.1 | Project Lead selection and contract | Whole Team | 2025-08-18 | 2025-08-22 | 4 | 100% | bar: WEEK 1 M to WEEK 1 F; WEEK 10 M to WEEK 10 W
1.2 | Research | Whole Team | 2025-08-18 | 2025-09-12 | 24 | 100% | bar: WEEK 1 M to WEEK 4 F; WEEK 10 M to WEEK 10 W
1.3 | SOW and Perf Specs | Whole Team | 2025-08-19 | 2025-09-12 | 23 | 100% | bar: WEEK 1 T to WEEK 4 F; WEEK 10 M to WEEK 10 W
1.3.1 | Project Understanding complete and compare | Whole Team | 2025-08-19 | 2025-08-23 | 4 | 100% | bar: WEEK 1 T to WEEK 1 F; WEEK 10 M to WEEK 10 W
1.3.2 | Initial Statement of Work draft | Whole Team | 2025-08-20 | 2025-08-27 | 7 | 100% | bar: WEEK 1 W to WEEK 2 W; WEEK 10 M to WEEK 10 W
1.3.3 | Research Engr Standards | Whole Team | 2025-08-20 | 2025-09-12 | 22 | 100% | bar: WEEK 1 W to WEEK 4 F; WEEK 10 M to WEEK 10 W
1.3.4 | Kickoff Breakfast meeting | Whole Team | 2025-08-27 | 2025-08-27 | 0 | 100% | bar: WEEK 2 W; WEEK 10 M to WEEK 10 W
1.3.5 | Refine SOW and Project Specs | Whole Team | 2025-08-27 | 2025-09-09 | 12 | 100% | bar: WEEK 2 W to WEEK 4 T; WEEK 10 M to WEEK 10 W
1.3.6 | Meet Industry sponsors after kickoff breakfast | Whole Team | 2025-09-05 | 2025-09-05 | 0 | 100% | bar: WEEK 3 F; WEEK 10 M to WEEK 10 W
1.3.7 | Final SOW and Perf Specs | Whole Team | 2025-08-27 | 2025-09-12 | 15 | 100% | bar: WEEK 2 W to WEEK 4 F; WEEK 10 M to WEEK 10 W
2 | Conceptual Designs
2.1 | Electrical Dev Board concept dev. | Luke M. | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
2.2 | Electrical SDR Concept dev. | Luke M. | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
2.3 | IoT Application Use Cases | Whole Team | 2025-09-12 | 2025-09-22 | 10 | 100% | bar: WEEK 4 F to WEEK 6 M; WEEK 10 M to WEEK 10 W
2.4 | Mechanical SDR concept dev. | Ethan H. | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
2.5 | Computer Dev Board concept dev. | Alberto H. | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
2.6 | Computer SDR concept dev. | Alberto H. | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
3.6 | Demonstration design concept dev. | Whole Team | 2025-09-12 | 2025-09-26 | 14 | 100% | bar: WEEK 4 F to WEEK 6 F; WEEK 10 M to WEEK 10 W
3.4 | Prepare Decision Matrix | Whole Team | 2025-09-15 | 2025-09-18 | 3 | 100% | bar: WEEK 5 M to WEEK 5 R; WEEK 10 M to WEEK 10 W
2.6 | Prepare and practice CDR presentation | Whole Team | 2025-09-22 | 2025-09-26 | 4 | 100% | bar: WEEK 10 M to WEEK 10 W
2.7 | Research and Prepare BOM | Whole Team | 2025-09-18 | 2025-09-26 | 8 | 100% | bar: WEEK 5 R to WEEK 6 F; WEEK 10 M to WEEK 10 W
2.8 | CDR | Whole Team | 2025-09-26 | 2025-09-26 | 0 | 100% | bar: WEEK 6 F; WEEK 10 M to WEEK 10 W
3 | Project Design
3.1 | PCB Design | Luke M. | 2025-09-29 | 2025-10-29 | 30 | 100% | bar: WEEK 7 M to WEEK 11 W; WEEK 10 M to WEEK 10 W
3.2 | Enclosure Design | Ethan H. | 2025-09-29 | 2025-10-29 | 30 | 100% | bar: WEEK 7 M to WEEK 11 W; WEEK 10 M to WEEK 10 W
3.2.1 | IoT Protocol Logic | Kenneth L. | 2025-09-29 | 2025-10-29 | 30 | 100% | bar: WEEK 7 M to WEEK 11 W; WEEK 10 M to WEEK 10 W
3.2.2 | UI Flow | Alberto H. | 2025-09-29 | 2025-10-29 | 30 | 100% | bar: WEEK 7 M to WEEK 11 W; WEEK 10 M to WEEK 10 W
3.3 | Prepare and practice CDR presentation | Whole Team | 2025-10-29 | 2025-11-07 | 8 | 100% | bar: WEEK 11 W to WEEK 12 F; WEEK 10 M to WEEK 10 W
3.3.1 | PDR | Whole Team | 2025-11-07 | 2025-11-07 | 0 | 100% | bar: WEEK 12 F; WEEK 10 M to WEEK 10 W
3.4 | Parts Order | Ethan H. | 2025-11-07 | 2025-12-04 | 27 | 100% | bar: WEEK 12 F to WEEK 16 R; WEEK 10 M to WEEK 10 W
4 | Prototype Development
4.1 | PCB Development | Luke M. | 2026-01-12 | 2026-04-24 | 102 | 90% | bar: WEEK 1 M to WEEK 16 F
4.1a | PCB Revisions | Luke M. | 2026-01-12 | 2026-03-31 | 79 | 100% | bar: WEEK 1 M to WEEK 12 T
4.1b | Power Circuit Assembly | Luke M. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1c | Power Circuit Testing | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1d | SOC Circuit Assmebly | Luke M, | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1e | SOC Circuit Testing | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 75% | bar: WEEK 7 T to WEEK 10 W
4.1f | Antenna Assembly | Luke M. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1g | Antenna Testing | Luke M. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1h | Doorbell Circuit Assembly | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1i | Doorbell Circuit Testing | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 50% | bar: WEEK 7 T to WEEK 10 W
4.1j | Motion Sensor Circuit Assembly | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 90% | bar: WEEK 7 T to WEEK 10 W
4.1k | Motion Sensor Circuit Testing | Abdul B. | 2026-02-24 | 2026-03-18 | 24 | 50% | bar: WEEK 7 T to WEEK 10 W
4.1l | Microphone Circuit Assembly | Luke M. | 2026-02-24 | 2026-04-01 | 37 | 90% | bar: WEEK 7 T to WEEK 12 W
4.1m | Microphone Circuit Testing | Abdul B. | 2026-02-24 | 2026-04-01 | 37 | 50% | bar: WEEK 7 T to WEEK 12 W
4.1n | Speaker Circuit Assemby | Luke M. | 2026-02-24 | 2026-04-01 | 37 | 90% | bar: WEEK 7 T to WEEK 12 W
4.1o | Speaker Circuit Testing | Abdul B. | 2026-02-24 | 2026-04-01 | 37 | 50% | bar: WEEK 7 T to WEEK 12 W
4.1p | Final PCB Revisions | Luke M. | 2026-04-01 | 2026-04-24 | 23 | 100% | bar: WEEK 10 M to WEEK 10 W; WEEK 12 W to WEEK 16 F
4.2 | SoC Programming | Alberto H. | 2026-01-12 | 2026-04-13 | 91 | 83.33% | bar: WEEK 1 M to WEEK 14 M
4.2a | Doorbell Firmware | Alberto H. | 2026-01-12 | 2026-01-16 | 4 | 90% | bar: WEEK 1 M to WEEK 1 F; WEEK 10 M to WEEK 10 W
4.2b | Motion Sensor Firmware | Alberto H. | 2026-01-19 | 2026-01-23 | 4 | 90% | bar: WEEK 10 M to WEEK 10 W
4.2c | BLE Firmware | Alberto H. | 2026-01-26 | 2026-01-30 | 4 | 90% | bar: WEEK 3 M to WEEK 3 F; WEEK 10 M to WEEK 10 W
4.2d | Thread Firmware | Alberto H. | 2026-02-02 | 2026-03-20 | 48 | 80% | bar: WEEK 4 M to WEEK 10 F
4.2e | Microphone Firmware | Alberto H. | 2026-02-16 | 2026-04-06 | 50 | 75% | bar: WEEK 6 M to WEEK 13 M
4.2f | Speaker Firmware | Alberto H. | 2026-02-16 | 2026-04-13 | 57 | 75% | bar: WEEK 6 M to WEEK 14 M
4.3 | Gateway | Alberto H. | 2026-01-12 | 2026-04-01 | 79 | 90% | bar: WEEK 1 M to WEEK 12 W
4.3a | Gateway Pi Setup | Alberto H. | 2026-03-02 | 2026-03-06 | 4 | 90% | bar: WEEK 10 M to WEEK 10 W
4.3a | Gateway Dongle Configuration | Alberto H. | 2026-03-09 | 2026-03-13 | 4 | 90% | bar: WEEK 8 M to WEEK 10 W
4.4 | Node Red UI | Kenneth L. | 2026-02-16 | 2026-04-01 | 45 | 100% | bar: WEEK 6 M to WEEK 12 W
4.4a | Node-Red Motion Sensor UI Programing | Kenneth L. | 2026-02-16 | 2026-03-18 | 32 | 100% | bar: WEEK 6 M to WEEK 10 W
4.4b | Node-Red Doorbell UI Programing | Kenneth L. | 2026-02-16 | 2026-03-18 | 32 | 100% | bar: WEEK 6 M to WEEK 10 W
4.4c | Node-Red Speaker UI Programing | Kenneth L. | 2026-02-27 | 2026-04-01 | 34 | 100% | bar: WEEK 7 F to WEEK 12 W
4.4d | Security Login & Timeout UI Interface | Kenneth L. | 2026-02-23 | 2026-03-18 | 25 | 100% | bar: WEEK 7 M to WEEK 10 W
4.4e | Gateway Node-Red UI Integreation | Kenneth L. | 2026-02-16 | 2026-03-31 | 45 | 100% | bar: WEEK 6 M to WEEK 12 T
4.5 | User Interface Assembly | Abdul B | 2026-01-12 | 2026-01-19 | 7 | 100% | bar: WEEK 1 M to WEEK 2 M; WEEK 10 M to WEEK 10 W
4.6 | 3-D Printing | Ethan H. | 2026-01-12 | 2026-02-28 | 46 | 100% | bar: WEEK 1 M to WEEK 8 F; WEEK 10 M to WEEK 10 W
4.7 | Enclosure Assembly | Ethan H. | 2026-01-12 | 2026-02-28 | 46 | 95% | bar: WEEK 1 M to WEEK 8 F; WEEK 10 M to WEEK 10 W
4.8 | Testing and Verification | Whole Team | 2026-01-12 | 2026-04-24 | 102 | 50% | bar: WEEK 1 M to WEEK 16 F
4.9 | 30% Project Assembled | Whole Team | 2026-01-12 | 2026-02-20 | 38 | 100% | bar: WEEK 1 M to WEEK 6 F; WEEK 10 M to WEEK 10 W
4.10 | 90% Project Assembled | Whole Team | 2026-01-12 | 2026-03-18 | 66 | 100% | bar: WEEK 1 M to WEEK 10 W